## 2022 ANNUAL ACTION PLAN

| Programme (PBB) | Sub-Programme (PBB) | Broad Activities | Location | Time Frame (Quarters) |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Dept. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st | 2nd | 3rd | 4th | GoG | IGF | Others | New | On-going | Lead | Collaborating |
| Economic Development | Trade, Tourism and Industrial development | Organise One Study tour for 20 hair dressers. | Accra |  |  |  |  |  |  | 4,400.00 |  |  | BAC | DA/SMEs |
|  |  | Organise 4No. field visits to SMEs for counselling & follow-Ups for 50 SMEs | Asesewa, Fefe, Akateng |  |  |  |  |  | 3,500.00 |  |  |  | BAC | DA, GEA |
|  |  | Organise training on basic financial management for 50 SMEs and facilitate acquisition of loans | Asesewa |  |  |  |  |  | 2,000.00 |  |  |  | BAC/ NBSSI | DA, GEA, MASLOC |
|  |  | Organise community/association based sensitization, communication and Animation | Sisiamang, Mensah Dawa, Akateng, Asuom |  |  |  |  |  | 4,000.00 |  |  |  | BAC | DA, GEA |
|  |  | Organize occupational safety health & environmental Management (OSHEM) training for 45clients. | Asesewa |  |  |  |  | 2,000.00 | 2,000.00 |  |  |  | BAC | DA, GEA |
|  |  | Organise basic marketing training for 20 business owners | Asesewa |  |  |  |  |  | 2,500.00 |  |  |  | BAC | DA, GEA |
|  |  | Facilitate NVTI certificates acquisition for 50 graduates apprentices | Asesewa Akateng |  |  |  |  |  | 7,000.00 |  |  |  | BAC | DA, GEA |
|  |  | Organise 3No. Technology improvement trainings in charcoal making, cassava processing/packaging/branding & vegetable sellers for 20 women. | Sekesua Asesewa |  |  |  |  | 2,000.00 | 2,800.00 |  |  |  | BAC | DA, GEA, SMEs |
|  |  | Organise 2No. Business forum for SMEs |  |  |  |  |  |  |  | 3,500.00 |  |  | BAC | DA, GEA, SMEs |
|  |  | Construction of 1no market shed | Sekesua |  |  |  |  | 86,000.00 |  |  |  |  | Works | DA |
|  |  | Rehabilitation of 3No. Markets | Akateng Sekesua Akrusu |  |  |  |  | 50,000.00 |  |  |  |  | DWD | DA |
|  |  | Develop and market 3No. tourist sites |  |  |  |  |  | 20,000.00 |  |  |  |  | DA | Tourism Board |
|  | Agricultural Development | Provision of administrative support (Fuel & maintenance of 1 official vehicle and maintenance of 14 motorbikes) by December, 2022 | 4 zones |  |  |  |  | 12,884.60 |  | 6,000.00 |  |  | DAD | DA, |
|  |  | Provision of insurance cover for 1 official vehicle and 14 motorbikes by June, 2022 | 4 zones |  |  |  |  |  |  | 6,273 |  |  | DAD | SIC |
|  |  | Purchase of office materials & consumables by December, 2022 | District wide |  |  |  |  | 2,000.00 |  | 1005.20 |  |  | DAD | DA |
|  |  | Maintenance of office equipment by December, 2022 | District wide |  |  |  |  | 1,607.00 |  |  |  |  | DAD | DA |
|  |  | Procurement of PPEs for protection against COVID-19 by March 2022 | 4 zones |  |  |  |  |  |  | 500.00 |  |  | DAD | DA |
|  |  | Facilitate data collection on agricultural activities by purchasing 2 tablets by March 2022 | 4 zones |  |  |  |  |  |  | 2,000.00 |  |  | DAD | DA |
|  |  | Train 28 staff on best management practices in mango production by June, 2022 | 4 zones |  |  |  |  |  |  | 1,005.00 |  |  | DAD | DA |
|  |  | Train 28 staff on best husbandry practices (disease identification & nutrition) in livestock production by September, 2022 | 4 zones |  |  |  |  | 1,005.20 |  |  |  |  | DAD | DA |
|  |  | Train 28 staff on drying technologies for agricultural produce by June, 2022 | 4 zones |  |  |  |  | 1,005.20 |  |  |  |  | DAD | DA |
|  |  | Train 28 staff on FBO formation and operationalization by December 2022 | 4 zones |  |  |  |  |  |  | 1,005.20 |  |  | DAD | DA |
|  |  | Undertake monitoring visit to selected planned activity sites in the district by the District Coordinating Director and the District Chief Executive by December, 2022 | 4 zones |  |  |  |  |  |  | 4,000.00 |  |  | DAD | DA |
|  |  | Conduct supervision and monitoring visits to 10 operational areas by 7 DAOs and 1 DDA by December, 2022 | 4 zones |  |  |  |  | - | - | 16,800.00 |  |  | DAD | DA |
|  |  | Organize 12 monthly technical staff meetings for 28 staff by December, 2022 | District Wide |  |  |  |  | - | - | 5,075.25 |  |  | DAD | DA |
|  |  | Organize Research Extension Linkage Committee (RELC) meeting for 50 participants by June, 2022 | District Wide |  |  |  |  |  |  | 2,835.00 |  |  | DAD | DA |
|  |  | Coordinate and monitor government projects and programmes (PFJ, PERD, RFJ, SRI) by District Center for Agriculture, Commerce and Technology (DCACT) committee by December, 2022 | 4 zones |  |  |  |  |  |  | 1,620.46 |  |  | DAD | DA |
|  |  | Organize District Farmers' Day/National celebration by December, 2022 | District Wide |  |  |  |  | 50,000.00 | 70,000 |  |  |  | DAD | UMKDA |
|  |  | Carry out Multi Round Annual Crops and Livestock Survey (MRACLS) activities (Publicity, Listing, Data collection on crops and livestock, Yield studies etc.) in selected enumeration areas by December, 2022 | 4 zones |  |  |  |  |  |  | 2,750.00 |  |  | DAD | DA |
|  |  | Conduct 52 bi-weekly market survey by December 2022 | Asesewa market |  |  |  |  |  |  | 400.00 |  |  | DAD | DA |
|  |  | Collaborate with CRI to establish half acre demonstration each in two communities on varietal trials in sweet potato and cassava by June, 2022 | 2 Communities |  |  |  |  |  |  | 1,000.00 |  |  | DAD | RAD/CRI |
|  |  | Conduct two demonstrations in two zones on construction of simple housing units for livestock by September 2022 | 2 Zones |  |  |  |  |  |  | 1,000.00 |  |  | DAD | RAD/CRI |
|  |  | Organize 4 field days for 200 participants to demonstration sites by December 2022 |  |  |  |  |  |  |  | 2,500.00 |  |  | DAD | RAD/CRI |
|  |  | Undertake 2,912 home and farm visits by 7 AEAs to deliver existing & new technologies to farmers, FBOs and other clients by December, 2022 | 4 zones |  |  |  |  |  |  | 6,300.00 |  |  | DAD | DA |
|  |  | Sensitize 200 farmers in 10 operational areas on identification and control of Fall Army Worm by June 2022 | 4 zones |  |  |  |  | 2,582.83 |  |  |  |  | DAD | PPRSD |
|  |  | Collaborate with MOFAD to sensitize 50 fishermen in two fishing on fish farming by December 2022 | 2 zones |  |  |  |  | 705.00 |  |  |  |  | DAD | MOFAD |
|  |  | Sensitize 100 farmers in 4 zones on HIV/AIDS and Child Labour issues by December, 2022 | 4 zones |  |  |  |  | 1,268.67 |  |  |  |  | DAD | GHS |
|  |  | Train 50 farmers on snail farming (alternative livelihood activity) by September 2022 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD |  |
|  |  | Train 100 farmers in 4 zones on post-harvest management of cereals and legumes by December 2022 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD | DA |
|  |  | Hold a one-day food demonstration on nutrient rich foods in each of the four zones for 120 women in by December, 2022 | 4 zones |  |  |  |  |  |  | 2,995.30 |  |  | DAD | DA |
|  |  | Empower 40 women farmers in poultry production by September, 2022 | 4 zones |  |  |  |  |  |  | 6,823.00 |  |  | DAD | DA |
|  |  | Train 100 livestock farmers in 4 zones on animal nutrition by March, 2022 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD | DA |
|  |  | Conduct surveillance for scheduled livestock diseases and pest by December, 2022 | 4 zones |  |  |  |  |  |  | 2,000.00 |  |  | DAD | DA |
|  |  | Train two (2) gari processing FBOs on product labeling, packaging and branding by December 2022 | 2 Communities |  |  |  |  |  |  | 1,068.15 |  |  | DAD | FBOs |
|  |  | Train 100 farmers in 4 zones on climate smart agriculture by March 2022 | 4 Zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD | DA |
|  |  | Sensitize 100 farmers in 4 zones on bush fire prevention and control by December 2022 | 4 Zones |  |  |  |  | 1,268.67 |  |  |  |  | DAD | DA |
| Social Development | Education and Youth Development | Organize “my first day at school” ceremony in 45 schools | District Wide |  |  |  |  |  | 3,000.00 |  |  |  | GES | DA, |
|  |  | Organise Kindergarten Education Week celebration in the District | District Wide |  |  |  |  |  | 3,000.00 |  |  |  | GES | DA, |
|  |  | Conduct regular monitoring and supervision of all educational activities | District Wide |  |  |  |  |  | 5,000.00 |  |  |  | GES | DA, |
|  |  | Organise community sensitization on right age enrolment in 30 communities | District Wide |  |  |  |  |  |  | 20,000.00 |  |  | GES | DA, Unicef |
|  |  | Organise Capacity Building for teachers and GES Staff | District Wide |  |  |  |  | 250,000.00 |  |  |  |  | GES | JiCA, Unicef |
|  |  | Organize inter-schools sports and athletic competition (within and outside circuit and district) | District Wide |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA, |
|  |  | Procure hexagonal furniture, dual and mono desk | District Wide |  |  |  |  | 250,000.00 |  |  |  |  | DA | GES |
|  |  | Procure teaching and learning materials for SHS. | ASSEC |  |  |  |  | 150,000.00 |  |  |  |  | GES | DA, |
|  |  | Organise Science, Technology, Mathematics and Innovative Education (STIME) Clinic | District Wide |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA, |
|  |  | Organise quarterly DEOC meetings. | District Wide |  |  |  |  | 30,000.00 |  |  |  |  | GES | DA, |
|  |  | Organise BECE activities | District Wide |  |  |  |  | 75,000.00 |  |  |  |  | GES | DA, |
|  |  | Provide scholarship schemes to 100 needy pupils, especially those in deprived areas | District Wide |  |  |  |  | 100,000.00 |  |  |  |  | GES | DA, |
|  |  | Sensitise 40 communities to invest in children’s education | District Wide |  |  |  |  |  | 20,0000.00 |  |  |  | UNICEF | GES, DA |
|  |  | Construction of 1no. teachers quarters | AkumersuYiti |  |  |  |  |  |  | 150,000 |  |  | GES | DPs and DA |
|  |  | Construction of 1 No. 6 Unit classroom block with office and store, toilet and furniture | Akumersu Yiti |  |  |  |  | 102,164.96 |  |  |  |  | GES | DA |
|  |  | Construction of 1 No. teachers’ quarters with mechanized borehole | Akumersu Yiti |  |  |  |  | 55,603.94 |  |  |  |  | GES | DA |
|  |  | Renovation of Asesewa Anglican Primary School | Asesewa |  |  |  |  | 30,000.00 |  |  |  |  | GES | DWD |
|  |  | Construction of 3-unit Classroom Pavilion at Anglican School | Asesewa |  |  |  |  | 78,000.00 |  |  |  |  | GES | DWD |
|  |  | Construction of 1№ 6-unit Classroom Pavilion with Office and store | Nyoenyoem |  |  |  |  | 180,002.80 |  |  |  |  | GES | DA,DWD |
|  | Health Delivery | Fumigate, disinfect and maintain final disposal site. | Akateng |  |  |  |  | 105,000.00 |  |  |  |  | DEHU | Zoomlion Ghana DA |
|  |  | Procure 2No. Skip loaders sanitary tools and disinfectants/insecticides. | Asesewa -2 Akateng – 2 Otrokper – 2 Sekesua -2 |  |  |  |  | 160,000.00 | 65,000.00 |  |  |  | DEHU/ DPro | DA, Zoomlion Ghana |
|  |  | Organize food/drink Screening | District wide |  |  |  |  |  | 3,000.00 | - |  |  | DEHU | DA |
|  |  | Organise Public health education | District wide |  |  |  |  |  | 5,000.00 |  |  |  | DEHU | DA |
|  |  | Organise public education on Food safety and hygiene | District wide |  |  |  |  |  | 4,500.00 |  |  |  | DEHU | DA |
|  |  | Organize regular impounding of stray animals and enforcement of laws | District wide |  |  |  |  |  | 10,000.00 |  |  |  | DEHU | DA |
|  |  | Organize communal labour | Asesewa Akateng Otrokper Sekesua Akrusu Bias Junction |  |  |  |  | - | 8,000.00 | - |  |  | DEHU | DA |
|  |  | Rehabilitation of slaughter house at Akateng | Asesewa Akateng |  |  |  |  |  | 3,000.00 |  |  |  | DWD | DA |
|  |  | Connect 100Households to water facility | Asesewa |  |  |  |  | 70,000.00 |  |  |  |  | CWSA | UMKDA |
|  |  | Construction of isolation centre at Asesewa Gov’t Hospital | Asesewa |  |  |  |  | 30,000.00 |  |  |  |  | DHD | DA |
|  |  | Construction of CHPs Compound | Ponponya Fantem |  |  |  |  | 50,000.00 |  |  |  |  | DHD | DA |
|  |  | Construction of 1 No. CHPs compound (clinic) with mechanized bore hole | Kwabia Asasehene |  |  |  |  | 7,654.84 |  | 375,087.36 |  |  | GHS | DA |
|  |  | Construction of 1 No. CHPs compound (clinic) with mechanized bore hole | Bisa |  |  |  |  | 7,654.84 |  | 375,087.36 |  |  | DHD | DA |
|  |  | Construction of 1No Maternity ward with borehole | Esuom Manya |  |  |  |  | 79,933.32 |  | 319,733.28 |  |  | DHD | DA |
|  |  | Construction of 1No Maternity ward with borehole | Akateng |  |  |  |  | 79,933.32 |  | 319,733.24 |  |  | DHD | DA |
|  |  | Construction of 1No Nurses quarters with borehole | Esuom Manya |  |  |  |  | 55,964.14 |  | 223,856.56 |  |  | DHD | DA |
|  |  | Construction of 1No Nurses quarters with borehole | at Akateng |  |  |  |  | 55,964.14 |  | 223,856.56 |  |  | DHD | DA |
|  |  | Rehabilitation of 2No. CHPs Compounds |  |  |  |  |  | 50,000.00 |  |  |  |  | DHD | DA |
|  |  | Support COVID-19 response activities | District wide |  |  |  |  | 12,000.00 |  |  |  |  | DHD/ DA | DA |
|  |  | Organise HIV&AIDS activities | District wide |  |  |  |  | 8,000.00 |  |  |  |  | DHD/ DA | DAC |
|  | Social Welfare and Community Development | Organise mass meeting in 60 communities on child trafficking, child labour, child neglect, and child abuse | selected communities |  |  |  |  | 1,220.00 | 2,000.00 | 10,000.00 |  |  | DSWCD | UMKDA |
|  |  | Organise sensitization for 10 study groups in 10 communities on home management | selected communities |  |  |  |  | 1,992.00 | 1,000.00 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  | Organise training and support 4 women’s groups on business dynamics | Selected communities |  |  |  |  | 3,200.00 | 5,000.00 | 20,000.00 |  |  | DSWCD | UMKDA |
|  |  | Offer social welfare services to 20 families including case management | District wide |  |  |  |  |  |  | 20,000.00 |  |  | DSWCD | UMKDA |
|  |  | Engage 20 communities with the child protection tool kits | selected communities |  |  |  |  | 2,080.00 | 2,000.00 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  | Organise case management training in 5 communities | Selected communities |  |  |  |  | 4,550.00 | 1,000.00 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  | Support for intersect oral social services | District wide |  |  |  |  | 4,650.00 | 5,000.00 | 10,000.00 |  |  | DSWCD | UMKDA |
|  |  | Sensitize the public on PWDs interventions, identify, register and assist 200 PWD in economic activities | District wide |  |  |  |  | 15,000.00 | 5,000.00 | 400,000.00 |  |  | DSWCD | UMKDA |
|  | Birth and Death Registration Services | Register births and deaths | District wide |  |  |  |  |  | 9,000.00 |  |  |  | BND registry | DA, Dist. Hospital, CHPS, TBA |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Document all assembly/govt. lands | District wide |  |  |  |  |  | 20,000.00 |  |  |  | PPD | DA |
|  |  | Organize 4 number plan education programmes | District Wide |  |  |  |  |  | 8,000.00 |  |  |  | PPD | DA |
|  |  | Complete Street Naming and Property Addressing | Asesewa, Akateng Sekesua |  |  |  |  | 100,000.00 |  |  |  |  | PPD | DA |
|  |  | Organise Monthly Spatial Committee meetings | UMKDA |  |  |  |  | 100,000.00 | 80,000.00 |  |  |  | PPD | DA |
|  |  | Acquire Auto maps for the district | Asesewa |  |  |  |  | 8,000.00 |  |  |  |  | PPD | DA |
|  |  | Prepare comprehensive schemes layouts for major towns | Asesewa, |  |  |  |  | 10,000.00 | 10,000.00 |  |  |  | PPD | DA |
|  | Infrastructure Development | Completion of 3storey Office complex | UMKDA |  |  |  |  | 200,000.00 |  |  |  |  | DWD | DA |
|  |  | Construction of 1no. Magistrate court | Asesewa |  |  |  |  | 150,000.00 |  |  |  |  | DWD | DA |
|  |  | Construction of 1no Bungalow for District Magistrate | Asesewa |  |  |  |  | 50,000.00 |  |  |  |  | DWD | DA |
|  |  | Construction of 1no. Ambulance B ay and 4no. parking Lots for the upper Manya Krobo District Assembly | Asesewa |  |  |  |  | 70,826.00 |  |  |  |  | DWD | DA |
|  |  | Construction of washroom facilities for Upper Manya Krobo District Assembly (Old Block) | Asesewa |  |  |  |  | 78,417.60 |  |  |  |  | DWD | DA |
|  |  | Renovation and partition of office for Upper Manya Krobo District Assembly (Old Block) | Asesewa |  |  |  |  | 35,716.28 |  |  |  |  | DWD | DA |
|  |  | Renovation works at the DCE, DCD’s office | Asesewa |  |  |  |  | 59,836.00 |  |  |  |  | DWD | DA |
|  |  | Rehabilitation of 3No. Markets | Akateng Sekesua Akrusu |  |  |  |  | 200,000.00 |  |  |  |  | DWD | DA |
|  |  | Construction of pavement at Asesewa lorry park phase I. | Asesewa |  |  |  |  | 50,000.00 |  |  |  |  | DWD | DA |
|  |  | Construction of 5no. culverts | District Wide |  |  |  |  | 50,000.00 |  |  |  |  | DWD | DA |
|  |  | Creation of 38.00km Asesewa and Sekesua Town roads | Asesewa and Sekesua |  |  |  |  | 339,725.00 |  |  |  |  | DWD | DA |
|  |  | Reshaping of Asesewa to Awoworsu Akrusu road | Asesewa to Awoworsu Akrusu |  |  |  |  | 76,800.00 |  |  |  |  | DWD | DA |
|  |  | Reshaping of Abuasa Junction through Akohia, Lagos, to Ovuganya Feeder Roads (7.20km) | Abuasa Junction through Akohia, Lagos, to Ovuganya |  |  |  |  | 72,680.00 |  |  |  |  | DWD | DA |
|  |  | Reshaping of Kwabia through Teryi and Teryi to Battorkope Feeder Roads (10.80km) | Kwabia through Teryi and Teryi to Battorkope |  |  |  |  | 78,000.00 |  |  |  |  | DWD | DA |
|  |  | Reshaping of Ovuganya through Kumakuma to Kwabia Feeder Roads (6.50km) | Ovuganya through Kumakuma to Kwabia |  |  |  |  | 83,000.00 |  |  |  |  | DWD | DA |
|  |  | Reshaping of 10km Adwenso/Nyakumase/Nyoenyoem Feeder Roads | Adwenso-Nyonyoem |  |  |  |  | 151,000.00 |  |  |  |  | DWD | DA |
|  |  | Const. of 4no Culverts at Konkoney Mermersi and Dzomoa | Konkoney Mermersi and Dzomoa |  |  |  |  | 100,000.00 |  |  |  |  | DWD | DA |
|  |  | Const. of Culvert at Brukum Kponya | Brukum Kponya |  |  |  |  | 20,000.00 |  |  |  |  | DWD | DA |
|  |  | Rehabilitation of Trawa – Trawa Junction Feeder Road (4.00km) | Trawa |  |  |  |  |  |  | 245,908.33 |  |  | DWD | DA |
|  |  | Facilitate the construction of a landing beach | Akateng |  |  |  |  | 150,000.00 |  |  |  |  | VRA | DA |
|  |  | Drilling of 6no. boreholes with hand pumps and concrete platform Drilling and construction of boreholes in selected communities | Akotoklo Agbom Akumersu Dawa Abordornya Akutey Fefe Asempanieye |  |  |  |  | 190,000 |  |  |  |  | DWD | DA |
|  |  | Facilitate the establishment and training of WATSAN Committees | Selected Communities |  |  |  |  |  | 5,000.00 |  |  |  | DWST | DA, CWSA |
|  |  | Repair of 10No. Boreholes | District Wide |  |  |  |  | 15,000.00 |  |  |  |  | DWD | DA |
|  |  | Supply of 800m³ of limestone waste to Asesewa Town Roads | Asesewa |  |  |  |  | 68,000.00 |  |  |  |  | DWD | DA |
|  |  | Implementation of the O&M Plan | District wide |  |  |  |  | 30,000.00 |  |  |  |  | DWD | DA |
|  |  | Facilitate the extension of electricity to newly developed areas and connecting rural communities to the national grid. | District wide |  |  |  |  | 50,000.00 |  |  |  |  | DWD | DA |
|  |  | Procurement and supply of 100No. Streetlights | District wide |  |  |  |  | 200,000.00 |  |  |  |  | DWD | DA |
| Environmental Management | Disaster Prevention and Management | Organise regular public education in Churches, market places, schools etc on effects of bush fires and deforestation. | Selected communities |  |  |  |  | 1,500.00 | 1,000.00 |  |  |  | NADMO | GFS |
|  |  | Support the formation and operation of DVGs in 20 communities | Selected communities |  |  |  |  | 1,000.00 | 1,000.00 |  |  |  | NADMO | DA |
|  |  | Organize tree planting exercises in 20 communities | Selected communities |  |  |  |  | 1,000.00 | 1,000.00 |  |  |  | NADMO | DA |
|  |  | Organize 4no talk shows on climate change and its adverse effects | Selected communities |  |  |  |  | 1,000.00 | 500.00 |  |  |  | NADMO | DA |
|  |  | Rehabilitation of small earth dam | Akrusu |  |  |  |  |  |  | 507,615.74 |  |  | GPSNP | DoA |
|  |  | Planting of 20ha of mangoes and oil palm plantation | Akrusu Anyaboni |  |  |  |  |  |  | 1,000,000 |  |  | GPSNP | DoA |
| Management and Administration | General Administration | Organise all Statutory Meetings of the Assembly |  |  |  |  |  | 40,000.00 | 45,000.00 |  |  |  | Mg’mt | DA |
|  |  | Procure logistics for revenue collectors | District wide |  |  |  |  | 20,000.00 |  |  |  |  | Finance Dept. | DA |
|  |  | Organise Capacity building for Assembly members and staff | UMKDA |  |  |  |  | 25,000.00 |  |  |  |  | HR | HoDs |
|  |  | Facilitate the establishment of District offices for Departments/Agencies (NHIS,NIA) | UMKDA |  |  |  |  | 20,000.00 |  |  |  |  | Mgt | DA |
|  |  | Procure office equipment, furniture and supplies. | UMKDA |  |  |  |  | 13,000.00 | 5,000.00 |  |  |  | DPro | DA |
|  |  | Support security, road safety and operationalization of police stations | Selected towns |  |  |  |  | 200,000.00 |  |  |  |  | DA | GPS |
|  |  | Revalue all landed properties in the district (commercial & residential) | District wide |  |  |  |  | 100,000.00 |  |  |  |  | Finance Dept. | Valuation Board |
|  |  | Install computerized billing and collection system | UMKDA |  |  |  |  |  | 80,000.00 |  |  |  | DoF | DA |
|  |  | Update Revenue Database | District wide |  |  |  |  |  | 10,000.00 |  |  |  | Budget Unit | DoF |
|  |  | Sensitize major communities on payment of Rates | District Wide |  |  |  |  |  | 3,000.00 |  |  |  | Budget Unit | DoF/ISD/ PPD |
|  |  | Undertake DPCU, M&E activities/programmes and 2023 AAP preparation | UMKDA |  |  |  |  | 13,000.00 |  |  |  |  | DP | DPCU |
|  |  | Preparation of 2023 District Fee-fixing & Composite Budget | UMKDA |  |  |  |  | 30,000.00 |  |  |  |  | BU | BC,DA |
|  |  | Prepare 4no quarterly progress Reports |  |  |  |  |  | 1,000.00 |  |  |  |  | DP | DPCU |
|  |  | Implementation of MP’s projects |  |  |  |  |  | 300,000.00 |  |  |  |  | MP | DA |
|  |  | Provide support for community initiated projects | UMKDA |  |  |  |  | 206,052.6 |  |  |  |  | DA | DPCU |
|  |  | Support Sub-structures |  |  |  |  |  | 82,421.00 |  |  |  |  |  | DA |
|  |  | Organize bi-annual social accountability meetings/Town Hall meetings | Selected Towns |  |  |  |  | 60,000.00 |  |  |  |  | BU | DPCU /HoDs |
|  |  | Organise civic education on responsive governance and citizens’ participation in development dialogue | District wide | 50 | 85 | 90 | 40 | 12,000.00 |  |  |  |  | NCCE | ISD,EC Media , DA,FBO, Legal Aid, CHRAJ, Political Parties, |
|  |  | Organise civic education in schools and identifiable groups on rights and responsibilities of citizens. | District wide | 50 | 85 | 90 | 40 | 13,000.00 |  |  |  |  | NCCE | GES, ISD, Media , DA, Legal Aid, CHRAJ, Political Parties,EC |
|  |  | Organise civic education on gender equality and equity in political, social and economic development | District wide | 60 | 80 | 90 | 60 | 21,000.00 |  |  |  |  | NCCE | GES, NGO, DOVSU, DSWCD, CHRAJ |

## 2023 Annual Action Plan

| Programme (PBB) | Sub-Programme (PBB) | Broad Activities | Location | Time Frame (Quarters) |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Dept. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st | 2nd | 3rd | 4th | GoG | IGF | Others | New | On-going | Lead | Collaborating |
| Economic Development | Trade, Tourism and Industrial development | Organise One Study tour for 20 hair dressers. |  |  |  |  |  |  |  | 4,400.00 |  |  | BAC | DA/SMEs |
|  |  | Organise 4No. field visits to SMEs for counselling & follow-Ups for 50 SMEs | Asesewa, Fefe, Akateng |  |  |  |  |  | 3,500.00 |  |  |  | BAC | DA, GEA |
|  |  | Organise training on basic financial management for 50 SMEs and facilitate acquisition of loans | Asesewa |  |  |  |  |  | 2,000.00 |  |  |  | BAC/ NBSSI | DA, GEA, MASLOC |
|  |  | Organise community/association based sensitization, communication and Animation | Sisiamang, Mensah Dawa, Akateng, Asuom |  |  |  |  |  | 4,000.00 |  |  |  | BAC | DA, GEA |
|  |  | Organize occupational safety health & environmental Management (OSHEM) training for 45clients. | Asesewa |  |  |  |  | 2,000.00 | 2,000.00 |  |  |  | BAC | DA, GEA |
|  |  | Organise basic marketing training for 20 business owners | Asesewa |  |  |  |  |  | 2,500.00 |  |  |  | BAC | DA, GEA |
|  |  | Facilitate NVTI certificates acquisition for 50 graduates apprentices | Asesewa Akateng |  |  |  |  |  | 7,000.00 |  |  |  | BAC | DA, GEA |
|  |  | Organise 3No. Technology improvement trainings in charcoal making, cassava processing/packaging/branding & vegetable sellers for 20 women. | Sekesua Asesewa |  |  |  |  | 2,000.00 | 2,800.00 |  |  |  | BAC | DA, GEA, SMEs |
|  |  | Organise 2No. Business forum for SMEs | UMKDA |  |  |  |  |  |  | 3,500.00 |  |  |  |  |
|  |  | Construction of 1no market shed | Sekesua |  |  |  |  | 86,000.00 |  |  |  |  | Works | DA |
|  |  | Rehabilitation of 3No. Markets | Akateng Sekesua Akrusu |  |  |  |  | 50,000.00 |  |  |  |  | DWD | DA |
|  |  | Develop and Market 3No. Tourist site |  |  |  |  |  | 20,000.00 |  |  |  |  |  |  |
|  | Agricultural Development | Provision of administrative support (Fuel & maintenance of 1 official vehicle and maintenance of 14 motorbikes) by December, 2023 | 4 zones |  |  |  |  | 12,884.60 |  | 6,000.00 |  |  | DAD | DA, |
|  |  | Provision of insurance cover for 1 official vehicle and 14 motorbikes by June, 2023 | 4 zones |  |  |  |  |  |  | 6,273.00 |  |  | DAD | SIC |
|  |  | Purchase of office materials & consumables by December, 2023 | District wide |  |  |  |  | 2,000.00 |  | 1,005.20 |  |  | DAD | DA |
|  |  | Maintenance of office equipment by December, 2023 | District wide |  |  |  |  | 1,607.00 |  |  |  |  | DAD | DA |
|  |  | Procurement of PPEs for protection against COVID-19 by March 2023 | 4 zones |  |  |  |  |  |  | 500.00 |  |  | DAD | DA |
|  |  | Facilitate data collection on agricultural activities by purchasing 2 tablets by March 2023 | 4 zones |  |  |  |  |  |  | 2,000.00 |  |  | DAD | DA |
|  |  | Train 28 staff on best management practices in mango production by June, 2023 | 4 zones |  |  |  |  |  |  | 1,005.00 |  |  | DAD | DA |
|  |  | Train 28 staff on best husbandry practices (disease identification & nutrition) in livestock production by September, 2023 | 4 zones |  |  |  |  | 1,005.20 |  |  |  |  | DAD | DA |
|  |  | Train 28 staff on drying technologies for agricultural produce by June, 2023 | 4 zones |  |  |  |  | 1,005.20 |  |  |  |  | DAD | DA |
|  |  | Train 28 staff on FBO formation and operationalization by December 2023 | 4 zones |  |  |  |  |  |  | 1,005.20 |  |  | DAD | DA |
|  |  | Undertake monitoring visit to selected planned activity sites in the district by the District Coordinating Director and the District Chief Executive by December, 2023 | 4 zones |  |  |  |  |  |  | 4,000.00 |  |  | DAD |  |
|  |  | Conduct supervision and monitoring visits to 10 operational areas by 7 DAOs and 1 DDA by December, 2023 | 4 zones |  |  |  |  | - | - | 16,800.00 |  |  | DAD | DA |
|  |  | Organize 12 monthly technical staff meetings for 28 staff by December, 2023 | District Wide |  |  |  |  | - | - | 5,075.25 |  |  | DAD | DA |
|  |  | Organize Research Extension Linkage Committee (RELC) meeting for 50 participants by June, 2023 | District Wide |  |  |  |  |  |  | 2,835.00 |  |  | DAD | DA |
|  |  | Coordinate and monitor government projects and programmes (PFJ, PERD, RFJ, SRI) by District Center for Agriculture, Commerce and Technology (DCACT) committee by December, 2023 | 4 zones |  |  |  |  |  |  | 1,620.46 |  |  | DAD | DA |
|  |  | Organize District Farmers' Day/National celebration by December, 2023 | District Wide |  |  |  |  | 50,000.00 | 70,000 |  |  |  | DAD | UMKDA |
|  |  | Carry out Multi Round Annual Crops and Livestock Survey (MRACLS) activities (Publicity, Listing, Data collection on crops and livestock, Yield studies etc.) in selected enumeration areas by December, 2023 | 4 zones |  |  |  |  |  |  | 2,750.00 |  |  | DAD | DA |
|  |  | Conduct 52 bi-weekly market survey by December 2023 | Asesewa market |  |  |  |  |  |  | 400.00 |  |  | DAD | DA |
|  |  | Collaborate with CRI to establish half acre demonstration each in two communities on varietal trials in sweet potato and cassava by June, 2023 | 2 Communities |  |  |  |  |  |  | 1,000.00 |  |  | DAD | RAD/CRI |
|  |  | Conduct two demonstrations in two zones on construction of simple housing units for livestock by September 2023 | 2 Zones |  |  |  |  |  |  | 1,000.00 |  |  | DAD | RAD/CRI |
|  |  | Organize 4 field days for 200 participants to demonstration sites by December 2023 |  |  |  |  |  |  |  | 2,500.00 |  |  | DAD | RAD/CRI |
|  |  | Undertake 2,912 home and farm visits by 7 AEAs to deliver existing & new technologies to farmers, FBOs and other clients by December, 2023 | 4 zones |  |  |  |  |  |  | 6,300.00 |  |  | DAD | DA |
|  |  | Sensitize 200 farmers in 10 operational areas on identification and control of Fall Army Worm by June 2023 | 4 zones |  |  |  |  | 2,582.83 |  |  |  |  | DAD | PPRSD |
|  |  | Collaborate with MOFAD to sensitize 50 fishermen in two fishing on fish farming by December 2023 | 2 zones |  |  |  |  | 705.00 |  |  |  |  | DAD | MOFAD |
|  |  | Sensitize 100 farmers in 4 zones on HIV/AIDS and Child Labour issues by December, 2023 | 4 zones |  |  |  |  | 1,268.67 |  |  |  |  | DAD | GHS |
|  |  | Train 50 farmers on snail farming (alternative livelihood activity) by September 2023 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD |  |
|  |  | Train 100 farmers in 4 zones on post-harvest management of cereals and legumes by December 2023 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD | DA |
|  |  | Hold a one-day food demonstration on nutrient rich foods in each of the four zones for 120 women in by December, 2023 | 4 zones |  |  |  |  |  |  | 2,995.30 |  |  | DAD | DA |
|  |  | Empower 40 women farmers in poultry production by September, 2023 | 4 zones |  |  |  |  |  |  | 6823.00 |  |  | DAD | DA |
|  |  | Train 100 livestock farmers in 4 zones on animal nutrition by March, 2023 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD | DA |
|  |  | Conduct surveillance for scheduled livestock diseases and pest by December, 2023 | 4 zones |  |  |  |  |  |  | 2,000.00 |  |  | DAD | DA |
|  |  | Train two (2) gari processing FBOs on product labeling, packaging and branding by December 2023 | 2 Communities |  |  |  |  |  |  | 1,068.15 |  |  | DAD | FBOs |
|  |  | Train 100 farmers in 4 zones on climate smart agriculture by March 2023 | 4 Zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD | DA |
|  |  | Sensitize 100 farmers in 4 zones on bush fire prevention and control by December 2023 | 4 Zones |  |  |  |  | 1,268.67 |  |  |  |  | DAD | DA |
| Social Development | Education and Youth Development | Organize “my first day at school” ceremony in 45 schools | District Wide |  |  |  |  |  | 3,000.00 |  |  |  | GES | DA, |
|  |  | Organise Kindergarten Education Week celebration in the District | District Wide |  |  |  |  |  | 3,000.00 |  |  |  | GES | DA, |
|  |  | Conduct regular monitoring and supervision of all educational activities | District Wide |  |  |  |  |  | 3,000.00 |  |  |  | GES | DA, |
|  |  | Organise community sensitization on right age enrolment in 30 communities | District Wide |  |  |  |  |  |  | 20,000.00 |  |  | GES | DA, |
|  |  | Organise Capacity Building for teachers and GES Staff | District Wide |  |  |  |  | 250,000.00 |  |  |  |  | GES | JiCA, Unicef |
|  |  | Organize inter-schools sports and athletic competition (within and outside circuit and district) | District Wide |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA, |
|  |  | Procure hexagonal furniture, dual and mono desk | District Wide |  |  |  |  | 250,000.00 |  |  |  |  | DA | GES |
|  |  | Procure teaching and learning materials for SHS. | ASSEC |  |  |  |  | 150,000.00 |  |  |  |  | GES | DA, |
|  |  | Organise Science, Technology, Mathematics and Innovative Education (STIME) Clinic | District Wide |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA, |
|  |  | Organise quarterly DEOC meetings. | District Wide |  |  |  |  | 30,000.00 |  |  |  |  | GES | DA, |
|  |  | Organise BECE activities | District Wide |  |  |  |  | 75,000.00 |  |  |  |  | GES | DA, |
|  |  | Provide scholarship schemes to 100 needy pupils, especially those in deprived areas | District Wide |  |  |  |  | 100,000.00 |  |  |  |  | GES | DA, |
|  |  | Sensitise 40 communities to invest in children’s education | District Wide |  |  |  |  |  | 20,0000.00 |  |  |  | UNICEF | GES, DA |
|  |  | Rehabilitation of 3No. 2Unit classrooms Block and 1No. 3unit Classroom Block. | Sekesua Bishop Andoh R/C KG, Battor Kope D/A KG & Breponsu Anglican |  |  |  |  | 60,000.00 |  |  |  |  | GES | DA |
|  |  | Rehabilitation of 4No. 6Unit Classroom Blocks | Trawa Manya D/A, Brukum Tsrebuana D/A Prim., Dzomoa R/C Prim., Konkoney R/C Prim. |  |  |  |  | 120,000.00 |  |  |  |  | GES | DA |
|  |  | Rehabilitation of 3No. 3Unit Classroom Blocks | Adwenso R/C JHS, Fefe Presby JHS, Akateng D/A JHS |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA |
|  |  | Construction of 5No. 2Unit KG Blocks with office, store and washrooms | Apimsu Presby, Trawa Manya D/A, Ternguanya R/C, Brukum Tsrebuana, Akotoe Tsrebuana D/A |  |  |  |  | 1,250,000.00 |  |  |  |  | GES | DA |
|  |  | Construction of 2No. 6Unit Classroom Block with office, store & washrooms. | Odomedji D/A Prim., Tibuorso R/C Prim. |  |  |  |  | 1,100,000.00 |  |  |  |  | GES | DA |
|  |  | Construction of 3No. 3Unit Classroom Block with office, store & washrooms. | Sekesua Djamam, Akotoe R/C JHS, Akrusu-Saisi R/C JHS |  |  |  |  | 1,200,000.00 |  |  |  |  | GES | DA |
|  | Health Delivery | Fumigate, disinfect and maintain final disposal site. | Akateng |  |  |  |  | 105,000.00 |  |  |  |  | DEHU | Zoomlion Ghana DA |
|  |  | Procure 2No. Skip loaders sanitary tools and disinfectants/insecticides. | Asesewa -2 Akateng – 2 Otrokper – 2 Sekesua -2 |  |  |  |  | 160,000.00 | 65,000.00 |  |  |  | DEHU/ DPro | DA, Zoomlion Ghana |
|  |  | Organize food/drink Screening | District wide |  |  |  |  |  | 3,000.00 | - |  |  | DEHU | DA |
|  |  | Organise Public health education | District wide |  |  |  |  |  | 5,000.00 |  |  |  | DEHU | DA |
|  |  | Organise public education on Food safety and hygiene | District wide |  |  |  |  |  | 4,500.00 |  |  |  | DEHU | DA |
|  |  | Organize regular impounding of stray animals and enforcement of laws | District wide |  |  |  |  |  | 10,000.00 |  |  |  | DEHU | DA |
|  |  | Organize communal labour | Asesewa Akateng Otrokper Sekesua Akrusu Bias Junction |  |  |  |  | - | 8,000.00 | - |  |  | DEHU | DA |
|  |  | Construction of slaughter house at Akateng | Asesewa Akateng |  |  |  |  |  | 3,000.00 |  |  |  | DWD | DA |
|  |  | Connect 100Households to water facility | Asesewa |  |  |  |  | 70,000.00 |  |  |  |  | CWSA | UMKDA |
|  |  | Construction of 4No. CHPS Compound | Akrusu, Akorkorma – Sisi, Aboatsam, Klumhe- Akontaa |  |  |  |  | 300,000.00 |  |  |  |  | DHD | DA |
|  |  | Rehabilitation of 2No. CHPs Compounds |  |  |  |  |  | 50,000.00 |  |  |  |  | DHD | DA |
|  |  | Support COVID-19 response activities | District wide |  |  |  |  | 12,000.00 |  |  |  |  | DHD/ DA | DA |
|  |  | Organise HIV&AIDS activities | District wide |  |  |  |  | 8,000.00 |  |  |  |  | DHD/ DA | DAC |
|  | Social Welfare and Community Development | Organise mass meeting in 60 communities on child trafficking, child labour, child neglect, and child abuse | selected communities |  |  |  |  | 1,220.00 | 2,000.00 | 10,000.00 |  |  | DSWCD | UMKDA |
|  |  | Organise sensitization for 10 study groups in 10 communities on home management | selected communities |  |  |  |  | 1,992.00 | 1,000.00 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  | Organise training and support 4 women’s groups on business dynamics | Selected communities |  |  |  |  | 3,200.00 | 5,000.00 | 20,000.00 |  |  | DSWCD | UMKDA |
|  |  | Offer social welfare services to 20 families including case management | District wide |  |  |  |  |  |  | 20,000.00 |  |  | DSWCD | UMKDA |
|  |  | Engage 20 communities with the child protection tool kits | selected communities |  |  |  |  | 2,080.00 | 2000.00 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  | Organise case management training in 5 communities | Selected communities |  |  |  |  | 4,550.00 | 1000.00 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  | Support for intersect oral social services | District wide |  |  |  |  | 4,650.00 | 5000.00 | 10,000.00 |  |  | DSWCD | UMKDA |
|  |  | Sensitize the public on PWDs interventions, identify, register and assist 200 PWD in economic activities | District wide |  |  |  |  | 15,000.00 | 5,000.00 | 400,000.00 |  |  | DSWCD | UMKDA |
|  | Birth and Death Registration Services | Register births and deaths | District wide |  |  |  |  |  | 9,000.00 |  |  |  | BND registry | DA, Dist. Hospital, CHPS, TBA |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Document all assembly/govt. lands | District wide |  |  |  |  |  | 20,000.00 |  |  |  | PPD | DA |
|  |  | Organize 4 number plan education programmes | District Wide |  |  |  |  |  | 8,000.00 |  |  |  | PPD | DA |
|  |  | Complete Street Naming and Property Addressing | Asesewa, Akateng Sekesua |  |  |  |  | 100,000.00 |  |  |  |  | PPD | DA |
|  |  | Organise Monthly Spatial Committee meetings | UMKDA |  |  |  |  | 100,000.00 | 80,000.00 |  |  |  | PPD | DA |
|  |  | Acquire Auto maps for the district | Sekesua and Akateng |  |  |  |  | 8,000.00 |  |  |  |  | PPD | DA |
|  |  | Prepare comprehensive schemes layouts for major towns | Sekesua and Akateng |  |  |  |  | 10,000.00 | 10,000.00 |  |  |  | PPD | DA |
|  | Infrastructure Development | Completion of 3storey Office complex | UMKDA |  |  |  |  | 200,000.00 |  |  |  |  | DWD | DA |
|  |  | Construction of 1No. Shed for satellite market |  |  |  |  |  | 20,000.00 |  |  |  |  | DWD | DA |
|  |  | Rehabilitation of 3No. Markets | Akateng Sekesua Akrusu |  |  |  |  | 50,000.00 |  |  |  |  | DWD | DA |
|  |  | Construction of 3no. culverts | Akotoe-Tsrebuana, Saisi, Adefe |  |  |  |  | 200,000.00 |  |  |  |  | DWD | DA |
|  |  | Facilitate the construction of a landing beach | Akateng |  |  |  |  | 150,000.00 |  |  |  |  | DWD | DA |
|  |  | Repair of 20No. Boreholes | District Wide |  |  |  |  | 20,000.00 |  |  |  |  | DWD | DA |
|  |  | Construction of 5No. Boreholes | Selected Communities, |  |  |  |  | 150,000.00 |  |  |  |  | DWD | DA |
|  |  | Implementation of the O&M Plan | District wide |  |  |  |  | 30,000.00 |  |  |  |  | DWD | DA |
|  |  | Reshaping of feeder roads | District Wide |  |  |  |  | 150,000.00 |  |  |  |  | DWD | DA |
|  |  | Facilitate the extension of electricity to newly developed areas. | District wide |  |  |  |  | 50,000.00 |  |  |  |  | DWD | DA |
|  |  | Procurement and supply of 100No. Streetlights |  |  |  |  |  | 200,000.00 |  |  |  |  | DWD | DA |
| Environmental Management | Disaster Prevention and Management | Organise regular public education in Churches, market places, schools etc on effects of bush fires and deforestation. | Selected communities |  |  |  |  | 1,500.00 | 1,000.00 |  |  |  | NADMO | GFS |
|  |  | Support the formation and operation of DVGs in 20 communities | Selected communities |  |  |  |  | 1,000.00 | 1,000.00 |  |  |  | NADMO | DA |
|  |  | Organize tree planting exercises in 20 communities | Selected communities |  |  |  |  | 1,000.00 | 1,000.00 |  |  |  | NADMO | DA |
|  |  | Organize 4no talk shows on climate change and its adverse effects | Selected communities |  |  |  |  | 1,000.00 | 500.00 |  |  |  | NADMO | DA |
| Management and Administration | General Administration | Organise all Statutory Meetings of the Assembly |  |  |  |  |  | 40,000.00 | 45,000.00 |  |  |  | Mg’mt | DA |
|  |  | Procure logistics for revenue collectors | District wide |  |  |  |  | 20,000.00 |  |  |  |  | Finance Dept. | DA |
|  |  | Organise Capacity building for Assembly members and staff | UMKDA |  |  |  |  | 25,000.00 |  |  |  |  | HR | HoDs |
|  |  | Facilitate the establishment of District offices for Departments/Agencies (NHIS, forestry) | UMKDA |  |  |  |  | 5,000.00 | 5,000.00 |  |  |  | Mgt | DA |
|  |  | Procure office equipment, furniture and supplies | UMKDA |  |  |  |  | 13,000.00 | 5,000.00 |  |  |  | DPro | DA |
|  |  | Support security, road safety and operationalization of police stations | Selected towns |  |  |  |  | 200,000.00 |  |  |  |  | DA | GPS |
|  |  | Revalue all landed properties in the district (commercial & residential) | District wide |  |  |  |  | 100,000.00 |  |  |  |  | Finance Dept. | Valuation Board |
|  |  | Update Revenue Database | District wide |  |  |  |  |  | 10,000.00 |  |  |  | Budget Unit | DoF |
|  |  | Sensitize major communities on payment of Rates | District Wide |  |  |  |  |  | 3,000.00 |  |  |  | Budget Unit | DoF/ISD/ PPD |
|  |  | Undertake DPCU, M&E activities/programmes and 2024 AAP preparation | UMKDA |  |  |  |  | 13,000.00 |  |  |  |  | DP | DPCU |
|  |  | Preparation of 2024 District Fee-fixing & Composite Budget | UMKDA |  |  |  |  | 30,000.00 |  |  |  |  | BU | BC,DA |
|  |  | Prepare 4no quarterly progress Reports |  |  |  |  |  | 1,000.00 |  |  |  |  | DP | DPCU |
|  |  | Implementation of MP’s projects |  |  |  |  |  | 300,000.00 |  |  |  |  | MP | DA |
|  |  | Provide support for community initiated projects | UMKDA |  |  |  |  | 206,052.6 |  |  |  |  | DA | DPCU |
|  |  | Support Sub-structures |  |  |  |  |  | 82,421.00 |  |  |  |  |  | DA |
|  |  | Organize bi-annual social accountability meetings/Town Hall meetings | Selected Towns |  |  |  |  | 60,000.00 |  |  |  |  | BU | DPCU /HoDs |
|  |  | Organise civic education on responsive governance and citizens’ participation in development dialogue | District wide | 50 | 85 | 90 | 40 | 12,000.00 |  |  |  |  | NCCE | ISD,EC Media , DA,FBO, Legal Aid, CHRAJ, Political Parties, |
|  |  | Organise civic education in schools and identifiable groups on rights and responsibilities of citizens. | District wide | 50 | 85 | 90 | 40 | 13,000.00 |  |  |  |  | NCCE | GES, ISD, Media , DA, Legal Aid, CHRAJ, Political Parties,EC |
|  |  | Organise civic education on gender equality and equity in political, social and economic development | District wide | 60 | 80 | 90 | 60 | 21,000.00 |  |  |  |  | NCCE | GES, NGO, DOVSU, DSWCD, CHRAJ |

## 2024 Annual Action Plan

| Programme (PBB) | Sub-Programme (PBB) | Broad Activities | Location | Time Frame (Quarters) |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Dept. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st | 2nd | 3rd | 4th | GoG | IGF | Others | New | On-going | Lead | Collaborating |
| Economic Development | Trade, Tourism and Industrial development | Organise One Study tour for 20 hair dressers. |  |  |  |  |  |  |  | 4,400.00 |  |  | BAC | DA/SMEs |
|  |  | Organise 4No. field visits to SMEs for counselling & follow-Ups for 50 SMEs | Asesewa, Fefe, Akateng |  |  |  |  |  | 3,500.00 |  |  |  | BAC | DA, GEA |
|  |  | Organise training on basic financial management for 50 SMEs and facilitate acquisition of loans | Asesewa |  |  |  |  |  | 2,000.00 |  |  |  | BAC/ NBSSI | DA, GEA, MASLOC |
|  |  | Organise community/association based sensitization, communication and Animation | Sisiamang, Mensah Dawa, Akateng, Asuom |  |  |  |  |  | 4,000.00 |  |  |  | BAC | DA, GEA |
|  |  | Organize occupational safety health & environmental Management (OSHEM) training for 45clients. | Asesewa |  |  |  |  | 2,000.00 | 2,000.00 |  |  |  | BAC | DA, GEA |
|  |  | Organise basic marketing training for 20 business owners | Asesewa |  |  |  |  |  | 2,500.00 |  |  |  | BAC | DA, GEA |
|  |  | Facilitate NVTI certificates acquisition for 50 graduates apprentices | Asesewa Akateng |  |  |  |  |  | 7,000.00 |  |  |  | BAC | DA, GEA |
|  |  | Organise 3No. Technology improvement trainings in charcoal making, cassava processing/packaging/branding & vegetable sellers for 20 women. | Sekesua Asesewa |  |  |  |  | 2,000.00 | 2,800.00 |  |  |  | BAC | DA, GEA, SMEs |
|  |  | Organise 2No. Business forum for SMEs | UMKDA |  |  |  |  |  |  | 3,500.00 |  |  |  |  |
|  |  | Construction of 1no market shed | Sekesua |  |  |  |  | 86,000 |  |  |  |  | Works | DA |
|  |  | Rehabilitation of 3No. Markets | Akateng Sekesua Akrusu |  |  |  |  | 50,000.00 |  |  |  |  | DWD | DA |
|  | Agricultural Development | Provision of administrative support (Fuel & maintenance of 1 official vehicle and maintenance of 14 motorbikes) by December, 2024 | 4 zones |  |  |  |  | 12,884.60 |  | 6,000.00 |  |  | DAD | DA, |
|  |  | Provision of insurance cover for 1 official vehicle and 14 motorbikes by June, 2023 | 4 zones |  |  |  |  |  |  | 6,273.00 |  |  | DAD | SIC |
|  |  | Purchase of office materials & consumables by December, 2024 | District wide |  |  |  |  | 2,000.00 |  | 1005.20 |  |  | DAD | DA |
|  |  | Maintenance of office equipment by December, 2024 | District wide |  |  |  |  | 1,607.00 |  |  |  |  | DAD | DA |
|  |  | Procurement of PPEs for protection against COVID-19 by March 2024 | 4 zones |  |  |  |  |  |  | 500.00 |  |  | DAD | DA |
|  |  | Facilitate data collection on agricultural activities by purchasing 2 tablets by March 2024 | 4 zones |  |  |  |  |  |  | 2,000.00 |  |  | DAD | DA |
|  |  | Train 28 staff on best management practices in mango production by June, 2024 | 4 zones |  |  |  |  |  |  | 1,005.00 |  |  | DAD | DA |
|  |  | Train 28 staff on best husbandry practices (disease identification & nutrition) in livestock production by September, 2024 | 4 zones |  |  |  |  | 1,005.20 |  |  |  |  | DAD | DA |
|  |  | Train 28 staff on drying technologies for agricultural produce by June, 2024 | 4 zones |  |  |  |  | 1,005.20 |  |  |  |  | DAD | DA |
|  |  | Train 28 staff on FBO formation and operationalization by December 2024 | 4 zones |  |  |  |  |  |  | 1,005.20 |  |  | DAD | DA |
|  |  | Undertake monitoring visit to selected planned activity sites in the district by the District Coordinating Director and the District Chief Executive by December, 2024 | 4 zones |  |  |  |  |  |  | 4,000.00 |  |  | DAD |  |
|  |  | Conduct supervision and monitoring visits to 10 operational areas by 7 DAOs and 1 DDA by December, 2024 | 4 zones |  |  |  |  | - | - | 16,800.00 |  |  | DAD | DA |
|  |  | Organize 12 monthly technical staff meetings for 28 staff by December, 2024 | District Wide |  |  |  |  | - | - | 5,075.25 |  |  | DAD | DA |
|  |  | Organize Research Extension Linkage Committee (RELC) meeting for 50 participants by June, 2024 | District Wide |  |  |  |  |  |  | 2,835.00 |  |  | DAD | DA |
|  |  | Coordinate and monitor government projects and programmes (PFJ, PERD, RFJ, SRI) by District Center for Agriculture, Commerce and Technology (DCACT) committee by December, 2024 | 4 zones |  |  |  |  |  |  | 1,620.46 |  |  | DAD | DA |
|  |  | Organize District Farmers' Day/National celebration by December, 2024 | District Wide |  |  |  |  | 50,000.00 | 70,000 |  |  |  | DAD | UMKDA |
|  |  | Carry out Multi Round Annual Crops and Livestock Survey (MRACLS) activities (Publicity, Listing, Data collection on crops and livestock, Yield studies etc.) in selected enumeration areas by December, 2024 | 4 zones |  |  |  |  |  |  | 2,750.00 |  |  | DAD | DA |
|  |  | Conduct 52 bi-weekly market survey by December 2023 | Asesewa market |  |  |  |  |  |  | 400.00 |  |  | DAD | DA |
|  |  | Collaborate with CRI to establish half acre demonstration each in two communities on varietal trials in sweet potato and cassava by June, 2024 | 2 Communities |  |  |  |  |  |  | 1,000.00 |  |  | DAD | RAD/CRI |
|  |  | Conduct two demonstrations in two zones on construction of simple housing units for livestock by September 2024 | 2 Zones |  |  |  |  |  |  | 1,000.00 |  |  | DAD | RAD/CRI |
|  |  | Organize 4 field days for 200 participants to demonstration sites by December 2024 |  |  |  |  |  |  |  | 2,500.00 |  |  | DAD | RAD/CRI |
|  |  | Undertake 2,912 home and farm visits by 7 AEAs to deliver existing & new technologies to farmers, FBOs and other clients by December, 2024 | 4 zones |  |  |  |  |  |  | 6,300.00 |  |  | DAD | DA |
|  |  | Sensitize 200 farmers in 10 operational areas on identification and control of Fall Army Worm by June 2024 | 4 zones |  |  |  |  | 2582.83 |  |  |  |  | DAD | PPRSD |
|  |  | Collaborate with MOFAD to sensitize 50 fishermen in two fishing on fish farming by December 2024 | 2 zones |  |  |  |  | 705.00 |  |  |  |  | DAD | MOFAD |
|  |  | Sensitize 100 farmers in 4 zones on HIV/AIDS and Child Labour issues by December, 2024 | 4 zones |  |  |  |  | 1,268.67 |  |  |  |  | DAD | GHS |
|  |  | Train 50 farmers on snail farming (alternative livelihood activity) by September 2024 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD |  |
|  |  | Train 100 farmers in 4 zones on post-harvest management of cereals and legumes by December 2024 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD | DA |
|  |  | Hold a one-day food demonstration on nutrient rich foods in each of the four zones for 120 women in by December, 2024 | 4 zones |  |  |  |  |  |  | 2,995.30 |  |  | DAD | DA |
|  |  | Empower 40 women farmers in poultry production by September, 2024 | 4 zones |  |  |  |  |  |  | 6,823.00 |  |  | DAD | DA |
|  |  | Train 100 livestock farmers in 4 zones on animal nutrition by March, 2024 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD | DA |
|  |  | Conduct surveillance for scheduled livestock diseases and pest by December, 2024 | 4 zones |  |  |  |  |  |  | 2,000.00 |  |  | DAD | DA |
|  |  | Train two (2) gari processing FBOs on product labeling, packaging and branding by December 2024 | 2 Communities |  |  |  |  |  |  | 1,068.15 |  |  | DAD | FBOs |
|  |  | Train 100 farmers in 4 zones on climate smart agriculture by March 2024 | 4 Zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD | DA |
|  |  | Sensitize 100 farmers in 4 zones on bush fire prevention and control by December 2024 | 4 Zones |  |  |  |  | 1,268.67 |  |  |  |  | DAD | DA |
| Social Development | Education and Youth Development | Organize “my first day at school” ceremony in 45 schools | District Wide |  |  |  |  |  | 3,000.00 |  |  |  | GES | DA, |
|  |  | Organise Kindergarten Education Week celebration in the District | District Wide |  |  |  |  |  | 3,000.00 |  |  |  | GES | DA, |
|  |  | Conduct regular monitoring and supervision of all educational activities | District Wide |  |  |  |  |  | 5,000.00 |  |  |  | GES | DA, |
|  |  | Organise community sensitization on right age enrolment in 30 communities | District Wide |  |  |  |  |  |  | 20,000.00 |  |  | GES | DA, |
|  |  | Organise Capacity Building for teachers and GES Staff | District Wide |  |  |  |  | 250,000.00 |  |  |  |  | GES | JiCA, Unicef |
|  |  | Organize inter-schools sports and athletic competition (within and outside circuit and district) | District Wide |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA, |
|  |  | Procure hexagonal furniture, dual and mono desk | District Wide |  |  |  |  | 250,000.00 |  |  |  |  | DA | GES |
|  |  | Procure teaching and learning materials for SHS. | ASSEC |  |  |  |  | 150,000.00 |  |  |  |  | GES | DA, |
|  |  | Organise Science, Technology, Mathematics and Innovative Education (STIME) Clinic | District Wide |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA, |
|  |  | Organise quarterly DEOC meetings. | District Wide |  |  |  |  | 30,000.00 |  |  |  |  | GES | DA, |
|  |  | Organise BECE activities | District Wide |  |  |  |  | 75,000.00 |  |  |  |  | GES | DA, |
|  |  | Provide scholarship schemes to 100 needy pupils, especially those in deprived areas | District Wide |  |  |  |  | 100,000.00 |  |  |  |  | GES | DA, |
|  |  | Sensitise 40 communities to invest in children’s education | District Wide |  |  |  |  |  | 20,000.00 |  |  |  | UNICEF | GES, DA |
|  |  | Rehabilitation of 3No. 2Unit Classroom Block | Selected schools |  |  |  |  | 60,000.00 |  |  |  |  | GES | DA |
|  |  | Rehabilitation of 4No. 6Unit Classroom Blocks | Selected schools |  |  |  |  | 120,000.00 |  |  |  |  | GES | DA |
|  |  | Rehabilitation of 3No. 3Unit Classroom Blocks |  |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA |
|  |  | Construction of 5No. 2Unit KG Blocks with office, store and washrooms | Akrusu-Saisi R/C KG, Aworworso Kpeti D/A KG, Bisa Presby KG, Bormase Ternya R/C KG, Brukum-Kponya D/A KG |  |  |  |  | 1,250,000.00 |  |  |  |  | GES | DA |
|  |  | Construction of 2No. 6Unit Classroom Block with office, store & washrooms. | Bormase Ternya R/C, Nyoenyoem Presby Prim. |  |  |  |  | 1,100,000.00 |  |  |  |  | GES | DA |
|  |  | Construction of 4No. 3Unit Classroom Block with office, store & washrooms. | Agajajeter D/A JHS, Otrokpe Presby JHS, Sawa Yiti Presby JHS, Sekesua Djamam |  |  |  |  | 1,600,000.00 |  |  |  |  | GES | DA |
|  | Health Delivery | Fumigate, disinfect and maintain final disposal site. | Akateng |  |  |  |  | 105,000.00 |  |  |  |  | DEHU | Zoomlion Ghana DA |
|  |  | Procure 2No. Skip loaders sanitary tools and disinfectants/insecticides. | Asesewa -2 Akateng – 2 Otrokper – 2 Sekesua -2 |  |  |  |  | 160,000.00 | 65,000.00 |  |  |  | DEHU/ DPro | DA, Zoomlion Ghana |
|  |  | Organize food/drink Screening | District wide |  |  |  |  |  | 3,000.00 | - |  |  | DEHU | DA |
|  |  | Organise Public health education | District wide |  |  |  |  |  | 5,000.00 |  |  |  | DEHU | DA |
|  |  | Organise public education on Food safety and hygiene | District wide |  |  |  |  |  | 4,500.00 |  |  |  | DEHU | DA |
|  |  | Organize regular impounding of stray animals and enforcement of laws | District wide |  |  |  |  |  | 10,000.00 |  |  |  | DEHU | DA |
|  |  | Organize communal labour | Asesewa Akateng Otrokper Sekesua Akrusu Bias Junction |  |  |  |  | - | 8,000.00 | - |  |  | DEHU | DA |
|  |  | Rehabilitation of slaughter house at Akateng | Asesewa Akateng |  |  |  |  |  | 3,000.00 |  |  |  | DWD | DA |
|  |  | Connect 100Households to water facility | Asesewa |  |  |  |  | 70,000.00 |  |  |  |  | CWSA | UMKDA |
|  |  | Construction of 4No. CHPS Compound | Akrusu, Akorkorma – Sisi, Aboatsam, Klumhe- Akontaa |  |  |  |  | 300, 000.00 |  |  |  |  | DHD | DA |
|  |  | Rehabilitation of 2No. CHPs Compounds |  |  |  |  |  | 50,000.00 |  |  |  |  | DHD | DA |
|  |  | Support COVID-19 response activities | District wide |  |  |  |  | 12,000.00 |  |  |  |  | DHD/ DA | DA |
|  |  | Organise HIV&AIDS activities | District wide |  |  |  |  | 8,000.00 |  |  |  |  | DHD/ DA | DAC |
|  | Social Welfare and Community Development | Organise mass meeting in 60 communities on child trafficking, child labour, child neglect, and child abuse | selected communities |  |  |  |  | 1,220.00 | 2,000.00 | 10,000.00 |  |  | DSWCD | UMKDA |
|  |  | Organise sensitization for 10 study groups in 10 communities on home management | selected communities |  |  |  |  | 1,992.00 | 1,000.00 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  | Organise training and support 4 women’s groups on business dynamics | Selected communities |  |  |  |  | 3,200.00 | 5,000.00 | 20,000.00 |  |  | DSWCD | UMKDA |
|  |  | Offer social welfare services to 20 families including case management | District wide |  |  |  |  |  |  | 20,000.00 |  |  | DSWCD | UMKDA |
|  |  | Engage 20 communities with the child protection tool kits | selected communities |  |  |  |  | 2,080.00 | 2,000.00 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  | Organise case management training in 5 communities | Selected communities |  |  |  |  | 4,550.00 | 1000 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  | Support for intersect oral social services | District wide |  |  |  |  | 4,650.00 | 5000.00 | 10,000.00 |  |  | DSWCD | UMKDA |
|  |  | Sensitize the public on PWDs interventions, identify, register and assist 200 PWD in economic activities | District wide |  |  |  |  | 15,000.00 | 5,000.00 | 400,000.00 |  |  | DSWCD | UMKDA |
|  | Birth and Death Registration Services | Register births and deaths | District wide |  |  |  |  |  | 9,000.00 |  |  |  | BND registry | DA, Dist. Hospital, CHPS, TBA |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Document all assembly/govt. lands | District wide |  |  |  |  |  | 20,000.00 |  |  |  | PPD | DA |
|  |  | Organize 4 number plan education programmes | District Wide |  |  |  |  |  | 8,000.00 |  |  |  | PPD | DA |
|  |  | Complete Street Naming and Property Addressing | Asesewa, Akateng Sekesua |  |  |  |  | 100,000.00 |  |  |  |  | PPD | DA |
|  |  | Organise Monthly Spatial Committee meetings | UMKDA |  |  |  |  | 100,000.00 | 80,000.00 |  |  |  | PPD | DA |
|  |  | Acquire Auto maps for the district | Otrokpe |  |  |  |  | 8,000.00 |  |  |  |  | PPD | DA |
|  |  | Prepare comprehensive schemes layouts for major towns | Otrokpe |  |  |  |  | 10,000.00 | 10,000.00 |  |  |  | PPD | DA |
|  | Infrastructure Development | Completion of 3storey Office complex | UMKDA |  |  |  |  | 200,000.00 |  |  |  |  | DWD | DA |
|  |  | Construction of 1No. Shed for satellite market |  |  |  |  |  | 20,000.00 |  |  |  |  | DWD | DA |
|  |  | Rehabilitation of 3No. Markets | Akateng Sekesua Akrusu |  |  |  |  | 50,000.00 |  |  |  |  | DWD | DA |
|  |  | Construction of 3no. culverts | Akotoe-Tsrebuana, Saisi, Adefe |  |  |  |  | 200,000.00 |  |  |  |  | DWD | DA |
|  |  | Facilitate the construction of a landing beach | Akateng |  |  |  |  | 150,000.00 |  |  |  |  | DWD | DA |
|  |  | Repair of 20No. Boreholes | District Wide |  |  |  |  | 20,000.00 |  |  |  |  | DWD | DA |
|  |  | Construction of 5No. Boreholes | Selected Communities, |  |  |  |  | 150,000.00 |  |  |  |  | DWD | DA |
|  |  | Implementation of the O&M Plan | District wide |  |  |  |  | 30,000.00 |  |  |  |  | DWD | DA |
|  |  | Reshaping of feeder roads | District Wide |  |  |  |  | 150,000.00 |  |  |  |  | DWD | DA |
|  |  | Facilitate the extension of electricity to newly developed areas. | District wide |  |  |  |  | 50,000.00 |  |  |  |  | DWD | DA |
|  |  | Procurement and supply of 100No. Streetlights |  |  |  |  |  | 200,000.00 |  |  |  |  | DWD | DA |
| Environmental Management | Disaster Prevention and Management | Organise regular public education in Churches, market places, schools etc on effects of bush fires and deforestation. | Selected communities |  |  |  |  | 1,500.00 | 1,000.00 |  |  |  | NADMO | GFS |
|  |  | Support the formation and operation of DVGs in 20 communities | Selected communities |  |  |  |  | 1,000.00 | 1,000.00 |  |  |  | NADMO | DA |
|  |  | Organize tree planting exercises in 20 communities | Selected communities |  |  |  |  | 1,000.00 | 1,000.00 |  |  |  | NADMO | DA |
|  |  | Organize 4no talk shows on climate change and its adverse effects | Selected communities |  |  |  |  | 1,000.00 | 1,000.00 |  |  |  | NADMO | DA |
| Management and Administration | General Administration | Organise all Statutory Meetings of the Assembly |  |  |  |  |  | 40,000.00 | 45,000.00 |  |  |  | Mg’mt | DA |
|  |  | Procure logistics for revenue collectors | District wide |  |  |  |  | 20,000.00 |  |  |  |  | Finance Dept. | DA |
|  |  | Organise Capacity building for Assembly members and staff | UMKDA |  |  |  |  | 25,000.00 |  |  |  |  | HR | HoDs |
|  |  | Facilitate the establishment of District offices for Departments/Agencies (NHIS,NIA) | UMKDA |  |  |  |  | 20,000.00 |  |  |  |  | Mgt | DA |
|  |  | Procure office equipment, furniture and supplies | UMKDA |  |  |  |  | 13,000.00 | 5,000.00 |  |  |  | DPro | DA |
|  |  | Support security, road safety and operationalization of police stations | Selected towns |  |  |  |  | 200,000.00 |  |  |  |  | DA | GPS |
|  |  | Revalue all landed properties in the district (commercial & residential) | District wide |  |  |  |  | 100,000.00 |  |  |  |  | Finance Dept. | Valuation Board |
|  |  | Install computerized billing and collection system | UMKDA |  |  |  |  |  | 80,000.00 |  |  |  | DoF | DA |
|  |  | Update Revenue Database | District wide |  |  |  |  |  | 10,000.00 |  |  |  | Budget Unit | DoF |
|  |  | Sensitize major communities on payment of Rates | District Wide |  |  |  |  |  | 3,000.00 |  |  |  | Budget Unit | DoF/ISD/ PPD |
|  |  | Undertake DPCU, M&E activities/programmes and 2025 AAP preparation | UMKDA |  |  |  |  | 13,000.00 |  |  |  |  | DP | DPCU |
|  |  | Preparation of 2025 District Fee-fixing & Composite Budget | UMKDA |  |  |  |  | 30,000.00 |  |  |  |  | BU | BC,DA |
|  |  | Prepare 4no quarterly progress Reports |  |  |  |  |  | 1,000.00 |  |  |  |  | DP | DPCU |
|  |  | Implementation of MP’s projects |  |  |  |  |  | 300,000.00 |  |  |  |  | MP | DA |
|  |  | Provide support for community initiated projects | UMKDA |  |  |  |  | 206,052.60 |  |  |  |  | DA | DPCU |
|  |  | Support Sub-structures |  |  |  |  |  | 82,421.00 |  |  |  |  |  | DA |
|  |  | Organize bi-annual social accountability meetings/Town Hall meetings | Selected Towns |  |  |  |  | 60,000.00 |  |  |  |  | BU | DPCU /HoDs |
|  |  | Organise civic education on responsive governance and citizens’ participation in development dialogue | District wide | 50 | 85 | 90 | 40 | 12,000.00 |  |  |  |  | NCCE | ISD,EC Media , DA,FBO, Legal Aid, CHRAJ, Political Parties, |
|  |  | Organise civic education in schools and identifiable groups on rights and responsibilities of citizens. | District wide | 50 | 85 | 90 | 40 | 13,000.00 |  |  |  |  | NCCE | GES, ISD, Media , DA, Legal Aid, CHRAJ, Political Parties,EC |
|  |  | Organise civic education on gender equality and equity in political, social and economic development | District wide | 60 | 80 | 90 | 60 | 21,000.00 |  |  |  |  | NCCE | GES, NGO, DOVSU, DSWCD, CHRAJ |

## 2025 Annual Action Plan

| Programme (PBB) | Sub-Programme (PBB) | Broad Activities | Location | Time Frame (Quarters) |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Dept. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st | 2nd | 3rd | 4th | GoG | IGF | Others | New | On-going | Lead | Collaborating |
| Economic Development | Trade, Tourism and Industrial development | Organise One Study tour for 20 hair dressers. |  |  |  |  |  |  |  | 4,400.00 |  |  | BAC | DA/SMEs |
|  |  | Organise 4No. field visits to SMEs for counselling & follow-Ups for 50 SMEs | Asesewa, Fefe, Akateng |  |  |  |  |  | 3,500.00 |  |  |  | BAC | DA, GEA |
|  |  | Organise training on basic financial management for 50 SMEs and facilitate acquisition of loans | Asesewa |  |  |  |  |  | 2,000.00 |  |  |  | BAC/ NBSSI | DA, GEA, MASLOC |
|  |  | Organise community/association based sensitization, communication and Animation | Sisiamang, Mensah Dawa, Akateng, Asuom |  |  |  |  |  | 4,000.00 |  |  |  | BAC | DA, GEA |
|  |  | Organize occupational safety health & environmental Management (OSHEM) training for 45clients. | Asesewa |  |  |  |  | 2,000.00 | 2,000.00 |  |  |  | BAC | DA, GEA |
|  |  | Organise basic marketing training for 20 business owners | Asesewa |  |  |  |  |  | 2,500.00 |  |  |  | BAC | DA, GEA |
|  |  | Facilitate NVTI certificates acquisition for 50 graduates apprentices | Asesewa Akateng |  |  |  |  |  | 7,000.00 |  |  |  | BAC | DA, GEA |
|  |  | Organise 3No. Technology improvement trainings in charcoal making, cassava processing/packaging/branding & vegetable sellers for 20 women. | Sekesua Asesewa |  |  |  |  | 2,000.00 | 2,800.00 |  |  |  | BAC | DA, GEA, SMEs |
|  |  | Organise 2No. Business forum for SMEs | UMKDA |  |  |  |  |  |  | 3,500.00 |  |  |  |  |
|  |  | Construction of 1no market shed | Sekesua |  |  |  |  | 86,000.00 |  |  |  |  | Works | DA |
|  |  | Rehabilitation of 3No. Markets | Akateng Sekesua Akrusu |  |  |  |  | 50,000.00 |  |  |  |  | DWD | DA |
|  | Agricultural Development | Provision of administrative support (Fuel & maintenance of 1 official vehicle and maintenance of 14 motorbikes) by December, 2023 | 4 zones |  |  |  |  | 12,884.60 |  | 6,000.00 |  |  | DAD | DA, |
|  |  | Provision of insurance cover for 1 official vehicle and 14 motorbikes by June, 2023 | 4 zones |  |  |  |  |  |  | 6,273.00 |  |  | DAD | SIC |
|  |  | Purchase of office materials & consumables by December, 2023 | District wide |  |  |  |  | 2,000.00 |  | 1005.20 |  |  | DAD | DA |
|  |  | Maintenance of office equipment by December, 2023 | District wide |  |  |  |  | 1,607.00 |  |  |  |  | DAD | DA |
|  |  | Procurement of PPEs for protection against COVID-19 by March 2023 | 4 zones |  |  |  |  |  |  | 500.00 |  |  | DAD | DA |
|  |  | Facilitate data collection on agricultural activities by purchasing 2 tablets by March 2023 | 4 zones |  |  |  |  |  |  | 2,000.00 |  |  | DAD | DA |
|  |  | Train 28 staff on best management practices in mango production by June, 2023 | 4 zones |  |  |  |  |  |  | 1,005.00 |  |  | DAD | DA |
|  |  | Train 28 staff on best husbandry practices (disease identification & nutrition) in livestock production by September, 2023 | 4 zones |  |  |  |  | 1,005.20 |  |  |  |  | DAD | DA |
|  |  | Train 28 staff on drying technologies for agricultural produce by June, 2023 | 4 zones |  |  |  |  | 1,005.20 |  |  |  |  | DAD | DA |
|  |  | Train 28 staff on FBO formation and operationalization by December 2023 | 4 zones |  |  |  |  |  |  | 1,005.20 |  |  | DAD | DA |
|  |  | Undertake monitoring visit to selected planned activity sites in the district by the District Coordinating Director and the District Chief Executive by December, 2023 | 4 zones |  |  |  |  |  |  | 4,000.00 |  |  | DAD |  |
|  |  | Conduct supervision and monitoring visits to 10 operational areas by 7 DAOs and 1 DDA by December, 2023 | 4 zones |  |  |  |  | - | - | 16,800.00 |  |  | DAD | DA |
|  |  | Organize 12 monthly technical staff meetings for 28 staff by December, 2023 | District Wide |  |  |  |  | - | - | 5,075.25 |  |  | DAD | DA |
|  |  | Organize Research Extension Linkage Committee (RELC) meeting for 50 participants by June, 2023 | District Wide |  |  |  |  |  |  | 2,835.00 |  |  | DAD | DA |
|  |  | Coordinate and monitor government projects and programmes (PFJ, PERD, RFJ, SRI) by District Center for Agriculture, Commerce and Technology (DCACT) committee by December, 2023 | 4 zones |  |  |  |  |  |  | 1,620.46 |  |  | DAD | DA |
|  |  | Organize District Farmers' Day/National celebration by December, 2023 | District Wide |  |  |  |  | 50,000.00 | 70,000 |  |  |  | DAD | UMKDA |
|  |  | Carry out Multi Round Annual Crops and Livestock Survey (MRACLS) activities (Publicity, Listing, Data collection on crops and livestock, Yield studies etc.) in selected enumeration areas by December, 2023 | 4 zones |  |  |  |  |  |  | 2,750.00 |  |  | DAD | DA |
|  |  | Conduct 52 bi-weekly market survey by December 2023 | Asesewa market |  |  |  |  |  |  | 400.00 |  |  | DAD | DA |
|  |  | Collaborate with CRI to establish half acre demonstration each in two communities on varietal trials in sweet potato and cassava by June, 2023 | 2 Communities |  |  |  |  |  |  | 1,000.00 |  |  | DAD | RAD/CRI |
|  |  | Conduct two demonstrations in two zones on construction of simple housing units for livestock by September 2023 | 2 Zones |  |  |  |  |  |  | 1,000.00 |  |  | DAD | RAD/CRI |
|  |  | Organize 4 field days for 200 participants to demonstration sites by December 2023 |  |  |  |  |  |  |  | 2,500.00 |  |  | DAD | RAD/CRI |
|  |  | Undertake 2,912 home and farm visits by 7 AEAs to deliver existing & new technologies to farmers, FBOs and other clients by December, 2023 | 4 zones |  |  |  |  |  |  | 6,300.00 |  |  | DAD | DA |
|  |  | Sensitize 200 farmers in 10 operational areas on identification and control of Fall Army Worm by June 2023 | 4 zones |  |  |  |  | 2582.83 |  |  |  |  | DAD | PPRSD |
|  |  | Collaborate with MOFAD to sensitize 50 fishermen in two fishing on fish farming by December 2023 | 2 zones |  |  |  |  | 705.00 |  |  |  |  | DAD | MOFAD |
|  |  | Sensitize 100 farmers in 4 zones on HIV/AIDS and Child Labour issues by December, 2023 | 4 zones |  |  |  |  | 1,268.67 |  |  |  |  | DAD | GHS |
|  |  | Train 50 farmers on snail farming (alternative livelihood activity) by September 2023 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD |  |
|  |  | Train 100 farmers in 4 zones on post-harvest management of cereals and legumes by December 2023 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD | DA |
|  |  | Hold a one-day food demonstration on nutrient rich foods in each of the four zones for 120 women in by December, 2023 | 4 zones |  |  |  |  |  |  | 2,995.30 |  |  | DAD | DA |
|  |  | Empower 40 women farmers in poultry production by September, 2023 | 4 zones |  |  |  |  |  |  | 6823.00 |  |  | DAD | DA |
|  |  | Train 100 livestock farmers in 4 zones on animal nutrition by March, 2023 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD | DA |
|  |  | Conduct surveillance for scheduled livestock diseases and pest by December, 2023 | 4 zones |  |  |  |  |  |  | 2,000.00 |  |  | DAD | DA |
|  |  | Train two (2) gari processing FBOs on product labeling, packaging and branding by December 2023 | 2 Communities |  |  |  |  |  |  | 1,068.15 |  |  | DAD | FBOs |
|  |  | Train 100 farmers in 4 zones on climate smart agriculture by March 2023 | 4 Zones |  |  |  |  |  |  | 1,175.00 |  |  | DAD | DA |
|  |  | Sensitize 100 farmers in 4 zones on bush fire prevention and control by December 2023 | 4 Zones |  |  |  |  | 1,268.67 |  |  |  |  | DAD | DA |
| Social Development | Education and Youth Development | Organize “my first day at school” ceremony in 45 schools | District Wide |  |  |  |  |  | 3,000.00 |  |  |  | GES | DA, |
|  |  | Organise Kindergarten Education Week celebration in the District | District Wide |  |  |  |  |  | 3,000.00 |  |  |  | GES | DA, |
|  |  | Conduct regular monitoring and supervision of all educational activities | District Wide |  |  |  |  |  | 5,000.00 |  |  |  | GES | DA, |
|  |  | Organise community sensitization on right age enrolment in 30 communities | District Wide |  |  |  |  |  |  | 20,000.00 |  |  | GES | DA, |
|  |  | Organise Capacity Building for teachers and GES Staff | District Wide |  |  |  |  | 250,000.00 |  |  |  |  | GES | JiCA, Unicef |
|  |  | Organize inter-schools sports and athletic competition (within and outside circuit and district) | District Wide |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA, |
|  |  | Procure hexagonal furniture, dual and mono desk | District Wide |  |  |  |  | 250,000.00 |  |  |  |  | DA | GES |
|  |  | Procure teaching and learning materials for SHS. | ASSEC |  |  |  |  | 150,000.00 |  |  |  |  | GES | DA, |
|  |  | Organise Science, Technology, Mathematics and Innovative Education (STIME) Clinic | District Wide |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA, |
|  |  | Organise quarterly DEOC meetings. | District Wide |  |  |  |  | 30,000.00 |  |  |  |  | GES | DA, |
|  |  | Organise BECE activities | District Wide |  |  |  |  | 75,000.00 |  |  |  |  | GES | DA, |
|  |  | Provide scholarship schemes to 100 needy pupils, especially those in deprived areas | District Wide |  |  |  |  | 100,000.00 |  |  |  |  | GES | DA, |
|  |  | Sensitise 40 communities to invest in children’s education | District Wide |  |  |  |  |  | 20,0000.00 |  |  |  | UNICEF | GES, DA |
|  |  | Rehabilitation of 3No. 2Unit Classroom Block | Sekesua Bishop Andoh R/C, Battor Kope D/A Basic |  |  |  |  | 60,000.00 |  |  |  |  | DA | GES/ DWD |
|  |  | Rehabilitation of 4No. 6Unit Classroom Blocks | Trawa Manya D/A, Asekeso D/A Prim., Dzomoa R/C Prim., Konkoney R/C Prim. |  |  |  |  | 120,000.00 |  |  |  |  | DA | GES/ DWD |
|  |  | Rehabilitation of 3No. 3Unit Classroom Blocks | Adwenso R/C JHS, Fefe Presby JHS, Akateng D/A JHS |  |  |  |  | 50,000.00 |  |  |  |  | DA | GES/ DWD |
|  |  | Construction of 5No. 2Unit KG Blocks with office, store and washrooms | Agajajeter D/A, Asekeso D/A, Anyesu-Kpeti, Akumersu-Osonson, Akohia Anglican |  |  |  |  | 1,250,000.00 |  |  |  |  | DA | GES |
|  |  | Construction of 2No. 6Unit Classroom Block with office, store & washrooms. | Ketedorm D/A primary, Adensu Prim., Com’ty C Prim. + 3 |  |  |  |  | 1,100,000.00 |  |  |  |  | GES | DA |
|  |  | Construction of 3No. 3Unit Classroom Block with office, store & washrooms. | Kwabea R/C Basic, Akotoe Tsrebuana +1 |  |  |  |  | 1,200,000.00 |  |  |  |  | GES | DA |
|  | Health Delivery | Fumigate, disinfect and maintain final disposal site. | Akateng |  |  |  |  | 105,000.00 |  |  |  |  | DEHU | Zoomlion Ghana DA |
|  |  | Procure 2No. Skip loaders sanitary tools and disinfectants/insecticides. | Asesewa -2 Akateng – 2 Otrokper – 2 Sekesua -2 |  |  |  |  | 160,000.00 | 65,000.00 |  |  |  | DEHU/ DPro | DA, Zoomlion Ghana |
|  |  | Organize food/drink Screening | District wide |  |  |  |  |  | 3,000.00 | - |  |  | DEHU | DA |
|  |  | Organise Public health education | District wide |  |  |  |  |  | 5,000.00 |  |  |  | DEHU | DA |
|  |  | Organise public education on Food safety and hygiene | District wide |  |  |  |  |  | 4,500.00 |  |  |  | DEHU | DA |
|  |  | Organize regular impounding of stray animals and enforcement of laws | District wide |  |  |  |  |  | 10,000.00 |  |  |  | DEHU | DA |
|  |  | Organize communal labour | Asesewa Akateng Otrokper Sekesua Akrusu Bias Junction |  |  |  |  | - | 8,000.00 | - |  |  | DEHU | DA |
|  |  | Rehabilitation of slaughter house at Akateng | Asesewa Akateng |  |  |  |  |  | 3,000.00 |  |  |  | DWD | DA |
|  |  | Connect 100Households to water facility | Asesewa |  |  |  |  | 70,000.00 |  |  |  |  | CWSA | UMKDA |
|  |  | Construction of 4No. CHPS Compound | Akrusu, Akorkorma – Sisi, Aboatsam, Klumhe- Akontaa |  |  |  |  | 300,000.00 |  |  |  |  | DA | DHD |
|  |  | Rehabilitation of 2No. CHPs Compounds |  |  |  |  |  | 50,000.00 |  |  |  |  | DA | DHD |
|  |  | Support COVID-19 response activities | District wide |  |  |  |  | 12,000.00 |  |  |  |  | DHD/ DA | DA |
|  |  | Organise HIV&AIDS activities | District wide |  |  |  |  | 8,000.00 |  |  |  |  | DHD/ DA | DAC |
|  | Social Welfare and Community Development | Organise mass meeting in 60 communities on child trafficking, child labour, child neglect, and child abuse | selected communities |  |  |  |  | 1,220.00 | 2,000.00 | 10,000.00 |  |  | DSWCD | UMKDA |
|  |  | Organise sensitization for 10 study groups in 10 communities on home management | selected communities |  |  |  |  | 1,992.00 | 1,000.00 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  | Organise training and support 4 women’s groups on business dynamics | Selected communities |  |  |  |  | 3,200.00 | 5,000.00 | 20,000.00 |  |  | DSWCD | UMKDA |
|  |  | Offer social welfare services to 20 families including case management | District wide |  |  |  |  |  |  | 20,000.00 |  |  | DSWCD | UMKDA |
|  |  | Engage 20 communities with the child protection tool kits | selected communities |  |  |  |  | 2,080.00 | 2,000.00 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  | Organise case management training in 5 communities | Selected communities |  |  |  |  | 4,550.00 | 1,000.00 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  | Support for intersect oral social services | District wide |  |  |  |  | 4,650.00 | 5,000.00 | 10,000.00 |  |  | DSWCD | UMKDA |
|  |  | Sensitize the public on PWDs interventions, identify, register and assist 200 PWD in economic activities | District wide |  |  |  |  | 15,000.00 | 5,000.00 | 400,000.00 |  |  | DSWCD | UMKDA |
|  | Birth and Death Registration Services | Register births and deaths | District wide |  |  |  |  |  | 9,000.00 |  |  |  | BND registry | DA, Dist. Hospital, CHPS, TBA |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Document all assembly/govt. lands | District wide |  |  |  |  |  | 20,000.00 |  |  |  | PPD | DA |
|  |  | Organize 4 number plan education programmes | District Wide |  |  |  |  |  | 8,000.00 |  |  |  | PPD | DA |
|  |  | Complete Street Naming and Property Addressing | Asesewa, Akateng Sekesua |  |  |  |  | 100,000.00 |  |  |  |  | PPD | DA |
|  |  | Organise Monthly Spatial Committee meetings | UMKDA |  |  |  |  | 100,000.00 | 80,000.00 |  |  |  | PPD | DA |
|  |  | Acquire Auto maps for the district | Anyaboni |  |  |  |  | 8,000.00 |  |  |  |  | PPD | DA |
|  |  | Prepare comprehensive schemes layouts for major towns | Anyaboni |  |  |  |  | 10,000.00 | 10,000.00 |  |  |  | PPD | DA |
|  | Infrastructure Development | Completion of 3storey Office complex | UMKDA |  |  |  |  | 200,000.00 |  |  |  |  | DWD | DA |
|  |  | Construction of 1No. Shed for satellite market |  |  |  |  |  | 20,000.00 |  |  |  |  | DWD | DA |
|  |  | Rehabilitation of 3No. Markets | Akateng Sekesua Akrusu |  |  |  |  | 50,000.00 |  |  |  |  | DWD | DA |
|  |  | Construction of 3no. culverts | Akotoe-Tsrebuana, Saisi, Adefe |  |  |  |  | 200,000.00 |  |  |  |  | DWD | DA |
|  |  | Facilitate the construction of a landing beach | Akateng |  |  |  |  | 150,000.00 |  |  |  |  | DWD | DA |
|  |  | Repair of 20No. Boreholes | District Wide |  |  |  |  | 20,000.00 |  |  |  |  | DWD | DA |
|  |  | Construction of 5No. Boreholes | Selected Communities, |  |  |  |  | 150,000.00 |  |  |  |  |  |  |
|  |  | Implementation of the O&M Plan | District wide |  |  |  |  | 30,000.00 |  |  |  |  | DWD | DA |
|  |  | Reshaping of feeder roads | District Wide |  |  |  |  | 150,000.00 |  |  |  |  | DWD | DA |
|  |  | Facilitate the extension of electricity to newly developed areas. | District wide |  |  |  |  | 50,000.00 |  |  |  |  | DWD | DA |
|  |  | Procurement and supply of 100No. Streetlights |  |  |  |  |  | 200,000.00 |  |  |  |  | DWD | DA |
| Environmental Management | Disaster Prevention and Management | Organise regular public education in Churches, market places, schools etc on effects of bush fires and deforestation. | Selected communities |  |  |  |  | 1,500.00 | 1,000.00 |  |  |  | NADMO | GFS |
|  |  | Support the formation and operation of DVGs in 20 communities | Selected communities |  |  |  |  | 1,000.00 | 1,000.00 |  |  |  | NADMO | DA |
|  |  | Organize tree planting exercises in 20 communities | Selected communities |  |  |  |  | 1,000.00 | 1,000.00 |  |  |  | NADMO | DA |
|  |  | Organize 4no talk shows on climate change and its adverse effects | Selected communities |  |  |  |  | 1,000.00 | 500.00 |  |  |  | NADMO | DA |
| Management and Administration | General Administration | Organise all Statutory Meetings of the Assembly |  |  |  |  |  | 40,000.00 | 45,000.00 |  |  |  | Mg’mt | DA |
|  |  | Procure logistics for revenue collectors | District wide |  |  |  |  | 20,000.00 |  |  |  |  | Finance Dept. | DA |
|  |  | Organise Capacity building for Assembly members and staff | UMKDA |  |  |  |  | 25,000.00 |  |  |  |  | HR | HoDs |
|  |  | Facilitate the establishment of District offices for Departments/Agencies (NHIS,NIA) | UMKDA |  |  |  |  | 20,000.00 |  |  |  |  | Mgt | DA |
|  |  | Procure office equipment, furniture and supplies | UMKDA |  |  |  |  | 13,000.00 | 5,000.00 |  |  |  | DPro | DA |
|  |  | Support security, road safety and operationalization of police stations | Selected towns |  |  |  |  | 200,000.00 |  |  |  |  | DA | GPS |
|  |  | Revalue all landed properties in the district (commercial & residential) | District wide |  |  |  |  | 100,000.00 |  |  |  |  | Finance Dept. | Valuation Board |
|  |  | Install computerized billing and collection system | UMKDA |  |  |  |  |  | 80,000.00 |  |  |  | DoF | DA |
|  |  | Update Revenue Database | District wide |  |  |  |  |  | 10,000.00 |  |  |  | Budget Unit | DoF |
|  |  | Sensitize major communities on payment of Rates | District Wide |  |  |  |  |  | 3,000.00 |  |  |  | Budget Unit | DoF/ISD/ PPD |
|  |  | Undertake DPCU, M&E activities/programmes and 2024 AAP preparation | UMKDA |  |  |  |  | 13,000.00 |  |  |  |  | DP | DPCU |
|  |  | Preparation of 2024 District Fee-fixing & Composite Budget | UMKDA |  |  |  |  | 30,000.00 |  |  |  |  | BU | BC,DA |
|  |  | Prepare 4no quarterly progress Reports |  |  |  |  |  | 1,000.00 |  |  |  |  | DP | DPCU |
|  |  | Implementation of MP’s projects |  |  |  |  |  | 300,000.00 |  |  |  |  | MP | DA |
|  |  | Provide support for community initiated projects | UMKDA |  |  |  |  | 206,052.6 |  |  |  |  | DA | DPCU |
|  |  | Support Sub-structures |  |  |  |  |  | 82,421.00 |  |  |  |  |  | DA |
|  |  | Organize bi-annual social accountability meetings/Town Hall meetings | Selected Towns |  |  |  |  | 60,000.00 |  |  |  |  | BU | DPCU /HoDs |
|  |  | Organise civic education on responsive governance and citizens’ participation in development dialogue | District wide | 50 | 85 | 90 | 40 | 12,000.00 |  |  |  |  | NCCE | ISD,EC Media , DA,FBO, Legal Aid, CHRAJ, Political Parties, |
|  |  | Organise civic education in schools and identifiable groups on rights and responsibilities of citizens. | District wide | 50 | 85 | 90 | 40 | 13,000.00 |  |  |  |  | NCCE | GES, ISD, Media , DA, Legal Aid, CHRAJ, Political Parties,EC |
|  |  | Organise civic education on gender equality and equity in political, social and economic development | District wide | 60 | 80 | 90 | 60 | 21,000.00 |  |  |  |  | NCCE | GES, NGO, DOVSU, DSWCD, CHRAJ |