UPPER MANYA KROBO DISTRICT ASSEMBLY

2022 COMPOSITE ANNUAL ACTION PLAN (AAP)

| Programme (PBB) | Sub-Programme (PBB) |  | Broad Activities | Location | Time Frame (Quarters) |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Dept. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | S/N |  |  | 1st | 2nd | 3rd | 4th | GoG | IGF | Others | New | On-going | Lead | Collaborating |
| Economic development | Trade, Tourism and Industrial development |  | Internal Management of the Department | BAC |  |  |  |  | 12,000.00 |  |  |  |  | BAC | BU,DF |
|  |  |  | Organise 4No. field visits to SMEs for counselling & follow-Ups for 50 clients | District wide |  |  |  |  | 4,400.00 |  |  |  |  | BAC | DA |
|  |  |  | Organise basic financial training for 50 clients on access to funds. | District wide |  |  |  |  | 3,500.00 |  |  |  |  | BAC | BU, DA |
|  |  |  | Organise basic marketing training for 20 business owners | District wide |  |  |  |  | 2,500.00 |  |  |  |  | BAC | BU, DA |
|  |  |  | Facilitate NVTI certificates acquisition for 50 graduates apprentices | District wide |  |  |  |  | 7,000.00 |  |  |  |  | BAC | BU, DA |
|  |  |  | Organise 3No. Technology improvement trainings in charcoal making, cassava processing/packaging/branding & vegetable sellers for 20 women. | District wide |  |  |  |  | 4,800.00 |  |  |  |  | BAC | DA |
|  |  |  | Organise One Study tour for 20 hair dressers. | District wide |  |  |  |  | 4,000.00 |  |  |  |  | BAC | DA |
|  |  |  | Establish District Tourism Committee and create access routes to 2no. tourist sites | Otrokper/ Akumersu |  |  |  |  | 50,000 |  |  |  |  | DA | DWD |
|  |  |  | Organize Second edition of Sisiamang stone city carnival | Sisiamng |  |  |  |  | 10,000.00 |  |  |  |  | DA | Trust FM, Klo Foundation |
| Economic Development | Agricultural Development |  | Provision of administrative support (Fuel & maintenance of 1 official vehicle and maintenance of 14 motorbikes) by December, 2022 | 4 zones |  |  |  |  | 12,884.60 |  | 6,000.00 |  |  | DoA | DA, |
|  |  |  | Provision of insurance cover for 1 official vehicle and 14 motorbikes by June, 2022 | 4 zones |  |  |  |  |  |  | 6,273 |  |  | DoA | SIC |
|  |  |  | Purchase of office materials & consumables by December, 2022 | District wide |  |  |  |  | 2,000.00 |  | 1005.20 |  |  | DoA | DA |
|  |  |  | Maintenance of office equipment by December, 2022 | District wide |  |  |  |  | 1,607.00 |  |  |  |  | DoA | DA |
|  |  |  | Procurement of PPEs for protection against COVID-19 by March 2022 | 4 zones |  |  |  |  |  |  | 500.00 |  |  | DoA | DA |
|  |  |  | Facilitate data collection on agricultural activities by purchasing 2 tablets by March 2022 | 4 zones |  |  |  |  |  |  | 2,000.00 |  |  | DoA | DA |
|  |  |  | Train 28 staff on best management practices in mango production by June, 2022 | 4 zones |  |  |  |  |  |  | 1,005.00 |  |  | DoA | DA |
|  |  |  | Train 28 staff on best husbandry practices (disease identification & nutrition) in livestock production by September, 2022 | 4 zones |  |  |  |  | 1,005.20 |  |  |  |  | DoA | DA |
|  |  |  | Train 28 staff on drying technologies for agricultural produce by June, 2022 | 4 zones |  |  |  |  | 1,005.20 |  |  |  |  | DoA | DA |
|  |  |  | Train 28 staff on FBO formation and operationalization by December 2022 | 4 zones |  |  |  |  |  |  | 1,005.20 |  |  | DoA | DA |
|  |  |  | Undertake monitoring visit to selected planned activity sites in the district by the District Coordinating Director and the District Chief Executive by December, 2022 | 4 zones |  |  |  |  |  |  | 4,000.00 |  |  | DoA |  |
|  |  |  | Conduct supervision and monitoring visits to 10 operational areas by 7 DAOs and 1 DDA by December, 2022 | 4 zones |  |  |  |  | - | - | 16,800.00 |  |  | DoA | DA |
|  |  |  | Organize 12 monthly technical staff meetings for 28 staff by December, 2022 | District Wide |  |  |  |  | - | - | 5,075.25 |  |  | DoA | DA |
|  |  |  | Organize Research Extension Linkage Committee (RELC) meeting for 50 participants by June, 2022 | District Wide |  |  |  |  |  |  | 2,835.00 |  |  | DoA | DA |
|  |  |  | Coordinate and monitor government projects and programmes (PFJ, PERD, RFJ, SRI) by District Center for Agriculture, Commerce and Technology (DCACT) committee by December, 2022 | 4 zones |  |  |  |  |  |  | 1,620.46 |  |  | DoA | DA |
|  |  |  | Organize District Farmers' Day/National celebration by December, 2022 | District Wide |  |  |  |  | 50,000.00 | 70,000 |  |  |  | DoA | UMKDA |
|  |  |  | Carry out Multi Round Annual Crops and Livestock Survey (MRACLS) activities (Publicity, Listing, Data collection on crops and livestock, Yield studies etc.) in selected enumeration areas by December, 2022 | 4 zones |  |  |  |  |  |  | 2,750.00 |  |  | DoA | DA |
|  |  |  | Conduct 52 bi-weekly market survey by December 2022 | Asesewa market |  |  |  |  |  |  | 400.00 |  |  | DoA | DA |
|  |  |  | Collaborate with CRI to establish half acre demonstration each in two communities on varietal trials in sweet potato and cassava by June, 2022 | 2 Communities |  |  |  |  |  |  | 1,000.00 |  |  | DoA | RAD/CRI |
|  |  |  | Collaborate with CRI to establish half acre demonstration each in two communities on fertilizer (Inorganic and organic) trial in maize and pepper production by June, 2022 | 2 Communities |  |  |  |  |  |  | 1,200.00 |  |  | DoA | RAD/CRI |
|  |  |  | Conduct two demonstrations in two zones on construction of simple housing units for livestock by September 2022 | 2 Zones |  |  |  |  |  |  | 1,000.00 |  |  | DoA | RAD/CRI |
|  |  |  | Organize 4 field days for 200 participants to demonstration sites by December 2022 |  |  |  |  |  |  |  | 2,500.00 |  |  | DoA | RAD/CRI |
|  |  |  | Undertake 2,912 home and farm visits by 7 AEAs to deliver existing & new technologies to farmers, FBOs and other clients by December, 2022 | 4 zones |  |  |  |  |  |  | 6,300.00 |  |  | DoA | DA |
|  |  |  | Sensitize 200 farmers in 10 operational areas on identification and control of Fall Army Worm by June 2022 | 4 zones |  |  |  |  | 2582.83 |  |  |  |  | DoA | PPRSD |
|  |  |  | Collaborate with MOFAD to sensitize 50 fishermen in two fishing on fish farming by December 2022 | 2 zones |  |  |  |  | 705.00 |  |  |  |  | DoA | MOFAD |
|  |  |  | Ssensitize 100 farmers in 4 zones on HIV/AIDS and Child Labour issues by December, 2022 | 4 zones |  |  |  |  | 1,268.67 |  |  |  |  | DoA | GHS |
|  |  |  | Train 50 farmers on snail farming (alternative livelihood activity) by September 2022 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DoA |  |
|  |  |  | Train 100 farmers in 4 zones on post-harvest management of cereals and legumes by December 2022 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DoA | DA |
|  |  |  | Hold a one-day food demonstration on nutrient rich foods in each of the four zones for 120 women in by December, 2022 | 4 zones |  |  |  |  |  |  | 2,995.30 |  |  | DoA | DA |
|  |  |  | Empower 40 women farmers in poultry production by September, 2022 | 4 zones |  |  |  |  |  |  | 6823.00 |  |  | DoA | DA |
|  |  |  | Train 100 livestock farmers in 4 zones on animal nutrition by March, 2022 | 4 zones |  |  |  |  |  |  | 1,175.00 |  |  | DoA | DA |
|  |  |  | Conduct surveillance for scheduled livestock diseases and pest by December, 2022 | 4 zones |  |  |  |  |  |  | 2,000.00 |  |  | DoA | DA |
|  |  |  | Train two (2) gari processing FBOs on product labeling, packaging and branding by December 2022 | 2 Communities |  |  |  |  |  |  | 1,068.15 |  |  | DoA | FBOs |
|  |  |  | Train 100 farmers in 4 zones on climate smart agriculture by March 2022 | 4 Zones |  |  |  |  |  |  | 1,175.00 |  |  | DoA | DA |
|  |  |  | Sensitize 100 farmers in 4 zones on bush fire prevention and control by December 2022 | 4 Zones |  |  |  |  | 1268.67 |  |  |  |  | DoA | DA |
|  |  |  | Construction of warehouse (1D1F) | Anyaboni |  |  |  |  |  |  |  |  |  |  |  |
| Social Development | Social Welfare and community Development |  | Organise mass meetings in 60 communities on child trafficking, child labour, child neglect, and child abuse | 60 selected communities |  |  |  |  | 1,220.00 | 2,000.00 | 10,000.00 |  |  | DSWCD | UMKDA |
|  |  |  | Organise sensitization for 10 study groups in 10 communities on home management | 10 selected communities |  |  |  |  | 1,992.00 | 1,000.00 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  |  | Organise training and support 4 women’s groups on business dynamics | Selected communities |  |  |  |  | 3,200.00 | 5,000.00 | 20,000.00 |  |  | DSWCD | UMKDA |
|  |  |  | Offer social welfare services to 20 families including case management | District wide |  |  |  |  |  |  | 20,000.00 |  |  | DSWCD | UMKDA |
|  |  |  | Engage 20 communities with the child protection tool kits | 20 selected communities in the district |  |  |  |  | 2,080.00 | 2000.00 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  |  | Organise case management training in 5 communities | Selected 5 communities |  |  |  |  | 4,550.00 | 1000 | 5,000.00 |  |  | DSWCD | UMKDA |
|  |  |  | Support for inter-sectorial social services | District wide |  |  |  |  | 4,650.00 | 5000.00 | 10,000.00 |  |  | DSWCD | UMKDA |
|  |  |  | Sensitize the public on PWDs interventions, identify, register and assist 200 PWD in economic activities | District wide |  |  |  |  | 15,000.00 | 5,000.00 | 400,000.00 |  |  | DSWCD | UMKDA |
| Social Development |  |  | Organise civic education in schools and identifiable groups on the need for tolerance, peaceful coexistence. | District wide |  |  |  |  |  |  |  |  |  | NCCE | Media, DA, Pol.Parties, EC |
|  |  |  | Ensure responsive government and citizens participation in the development dialogue | District wide |  |  |  |  |  |  |  |  |  | NCCE | ISD, DA |
|  |  |  | Promote discipline in all aspects of life | District wide |  |  |  |  |  |  |  |  |  | NCCE | GES, ISD, DSWCD |
|  |  |  | Attain gender equality and equity in political, social and economic development | District wide |  |  |  |  |  |  |  |  |  | NCCE | GES DOVSU,NGO DSD CHRAJ |
| Social services delivery | Health delivery |  | Organise and supervise regular liquid waste management, fumigation, disinfection and disinfestation of markets, sanitary sites and final disposal site. | District wide |  |  |  |  | 65,000 | - | - |  |  | DEHU | Zoomlion Gh DA |
|  |  |  | Enforcement of by-laws on sanitation, stray animals and organise public education on excessive noise making, clean air, meat hygiene and environmentally friendly sand wining. | District wide |  |  |  |  | 50,000.00 |  |  |  |  | DEHU | Public toilet operators DA |
|  |  |  | Organize food/Drink Screening Exercise | District wide |  |  |  |  | - | 3,000.00 | - |  |  | DEHU | DA |
|  |  |  | Organize regular communal labour and clean up exercises | Asesewa Akateng Otrokper Sekesua Akrusu Bias Junction |  |  |  |  | - | 8,000.00 | - |  |  | DEHU | DA |
|  |  |  | Organise quarterly environmental/public health education programs. | District wide |  |  |  |  |  | 5,000.00 |  |  |  | DEHU | DA |
|  |  |  | Organise public education on food safety and hygiene | District wide |  |  |  |  |  | 4,500.00 |  |  |  | DEHU | DA |
|  |  |  | Rehabilitation of slaughter house | Asesewa Akateng |  |  |  |  |  | 10,000.00 |  |  |  | DWD | DA |
|  |  |  | Promotion of household latrine in 20 communities | District wide |  |  |  |  | 15,000.00 |  |  |  |  | DEHU | DA |
|  |  |  | Organise COVID-19 vaccination and education | District wide |  |  |  |  |  |  | 100,000.00 |  |  | GHS | DA |
|  |  |  | Undertake distribution of LLM nets and support malaria response initiative | District wide |  |  |  |  | 100,000.00 |  |  |  |  | GHS | DA |
|  |  |  | Immunize 4,432 of children under 5 | District wide |  |  |  |  |  |  |  |  |  | GHS | DA |
|  |  |  | Support HIV/AIDs and TB response intervention | Hospital, Selected communities |  |  |  |  |  |  |  |  | 39,000 | GHS | DA |
|  |  |  | Register births and deaths | District wide |  |  |  |  |  |  |  |  |  | BND | DA,GHS |
| Infrastructure Delivery and Management | Infrastructure Development |  | Extension of community water system to private applicants. | Asesewa | 25 | 25 | 25 | 25 |  | 70,000.00 |  |  |  | CWSA | UMKDA |
|  |  |  | Drilling, construction and maintenance of 10no & other existing boreholes and community water facility. | District wide |  |  |  |  |  |  |  |  |  | DWD, Growth Aid, CWSA | DA, |
|  |  |  | Construction of 6No. Boreholes with hand pumps and concrete platform, and 1No. Mechanised boreholes with overhead tank. | Nyoenyoem, Dzamoa, Djamam, Ternguanya, Samlesi, Djakane |  |  |  |  | 15,285.05 |  |  |  |  | DWD | DA, |
|  |  |  | Construction of 1No. Mechanised borehole. | Abertima |  |  |  |  | 400,000.00 |  |  |  |  | DWD | GetFund/ Growth Aid |
| Management and Administration | Finance and Revenue Mobilisation |  | Undertake monitoring/supervision of revenue collectors and facilitate recruitment and training of revenue collectors | District wide |  |  |  |  | 3,000.00 |  |  |  |  | DoF | HR,DA |
|  |  |  | Collection/update of revenue database and revaluation of properties |  |  |  |  |  |  | 5,000.00 |  |  |  | DoF/ BU | DPCU |
|  |  |  | Acquire and install revenue software for revenue data base |  |  |  |  |  | 30,000.00 | 20,000.00 |  |  |  | DoF | DA |
|  |  |  | Facilitate rehabilitation and operationalization of Market Stores |  |  |  |  |  |  | 23,000.00 |  |  |  | DoF | DA |
| Social Development | Education and Youth Development |  | Monitoring, tracking and Data Analysis of children with disabilities in 98 schools | District wide |  |  |  |  | 15,000.00 |  |  |  |  | GES | DA |
|  |  |  | Organise EAR/EYE screening in 98 schools | District wide |  |  |  |  | 18,000.00 |  |  |  |  | GES | DA |
|  |  |  | Undertake In- class support for children with special needs | District wide |  |  |  |  | 20,000.00 |  |  |  |  | DA | GES |
|  |  |  | Conduct assessment of children with special educational needs | District wide |  |  |  |  | 60,000.00 |  |  |  |  | GES | DA DSWCD |
|  |  |  | Sensitise 40 communities to invest in children’s education | Schools in the district |  |  |  |  | 90,000.00 |  |  |  |  | UNICEF | GES, Unicef |
|  |  |  | Organise community sensitization on right age enrolment in 30 communities | Schools in the district |  |  |  |  |  |  | 20,000.00 |  |  | GES | DA, |
|  |  |  | Organize enrolment drive in 98 communities | Selected school in communities |  |  |  |  | 25,000.00 |  |  |  |  | GES | DA |
|  |  |  | Organize “my first day at school” ceremony in 45 schools | Selected school in communities |  |  |  |  | 30,000.00 |  |  |  |  | GES | DA |
|  |  |  | Organise physical education workshop for 97 teachers | Schools in the district |  |  |  |  |  |  | 30,000.00 |  |  | GES | Unicef |
|  |  |  | Organize inter-schools sports and athletic competition (within and outside circuit and district) | District wide |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA |
|  |  |  | Procure and supply furniture (hexagonal, dual & mono desk) | Schools in need in the district |  |  |  |  | 300,000.00 |  |  |  |  | DA | GES |
|  |  |  | Organize community sensitization on equal attention to boys and girls by parents in 90 community | District wide |  |  |  |  |  |  | 50,000.00 |  |  | GES | Unicef |
|  |  |  | Organise female mentors activities (teachers, community women and older girls) to mentor girls | Communities with low enrolment in school |  |  |  |  |  |  | 56,000.00 |  |  | GES | Unicef |
|  |  |  | Establish girls’ clubs in 50 schools | Schools in the district |  |  |  |  | 25,000.00 |  |  |  |  | GES | UNICEF |
|  |  |  | Provide basic needs like uniforms, sandals, exercise books, mathematical sets etc. 600 pupils | Deprived schools in the District |  |  |  |  | 150,00.00 |  |  |  |  | GES | MoE |
|  |  |  | Provide scholarship schemes to 100 needy students, especially those in deprived areas | District wide |  |  |  |  | 100,000.00 |  |  |  |  | DA | GES, MP,VRA |
|  |  |  | Organize capacity building workshop for SHEP coordinators on sanitation, environment and safety system in 45 schools | Selected schools in the district |  |  |  |  | 50,000.00 |  |  |  |  | GES | Unicef |
|  |  |  | Organize deworming programme in school | All schools in the district |  |  |  |  |  |  | 10,000.00 |  |  | GHS | GES |
|  |  |  | Provide TLMs for teaching and learning in 110 schools | All schools in the district |  |  |  |  | 70,000.00 |  |  |  |  | GES | DA |
|  |  |  | Provide appropriate and culturally relevant reading materials in 100 schools | All schools in the district |  |  |  |  | 10,000.00 |  |  |  |  | GES | DA |
|  |  |  | Provide supplementary readers in English and Ghanaian language in 110 schools | All schools in the district |  |  |  |  |  |  |  |  |  | USAID | GES DA |
|  |  |  | Organise INSET on Early Childhood Education for 120 teachers | Primary schools the district |  |  |  |  | 55,00.00 |  |  |  |  | Unicef | GES |
|  |  |  | Organise INSET for teachers in Multi grade teaching in 10 schools | Asesewa |  |  |  |  |  |  | 90,000.00 |  |  | GES | Donor Agency |
|  |  |  | Organise a grade based INSET for P1-P3 teachers on Maths and Science for 50 teachers | Asesewa |  |  |  |  |  |  | 80,000.00 |  |  | Unicef | GES |
|  |  |  | Organize competition in literacy and numeracy for 98 upper primary school children | All Circuits |  |  |  |  | 30,000.00 |  |  |  |  | GES | DA |
|  |  |  | Organise leadership seminar for 136 curriculum leaders, 136 heads, circuit 8 supervisors and 10 district inspection teams | Asesewa |  |  |  |  |  |  | 60,000.00 |  |  | Unicef | GES |
|  |  |  | Organise INSET for Heads, SMC and PTA on resource mobilization and the roles in management of Basic schools | Asesewa |  |  |  |  |  |  | 70,000.00 |  |  | JICA | GES |
|  |  |  | Train 90 teachers to administer first aid in schools | Asesewa |  |  |  |  |  |  | 40,000.00 |  |  | GES | Unicef |
|  |  |  | Organise counselling clinics on STI(Sexually Transmitted Infections) 110 in schools | In selected schools |  |  |  |  |  |  | 45,000.00 |  |  | Unicef | GES |
|  |  |  | Organise Best Teacher, worker Awards | Asesewa |  |  |  |  | 100,000.00 |  |  |  |  | GES | DA |
|  |  |  | Conduct staffing assessment in 98 schools | All schools in the district |  |  |  |  | 30,000.00 |  |  |  |  | GES | DA |
|  |  |  | Support the conduct of teacher appraiser for 1225 teachers | All school in the district |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA |
|  |  |  | Conduct regular monitoring and inspection of schools | All school in the district |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA |
|  |  |  | Organize capacity building workshop for guidance and counselling coordinators | Asesewa |  |  |  |  | 40,000.00 |  |  |  |  | GES | Unicef |
|  |  |  | Provide computers to teachers in all schools | All school in the district |  |  |  |  | 2,243,550.75 |  |  |  |  | GES | KA Technology |
|  |  |  | Organize capacity building workshop for teachers in ICT | Asesewa |  |  |  |  | 100,000.00 |  |  |  |  | GES | KA Technology |
|  |  |  | Organise Science, Technology, Mathematics and Innovative Education (STIME) Clinic | District |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA |
|  |  |  | Conduct SPAM in 110 schools | Designated schools |  |  |  |  |  |  | 90,000.00 |  |  | GES | UNICEF/JICA |
|  |  |  | Organize community SPAMs in 130 communities | All school communities |  |  |  |  |  |  | 100,000.00 |  |  | GES | Unicef/JICA |
|  |  |  | Supplement school grant with products from school farm and IGF. | Asesewa |  |  |  |  | 3,000.00 | 40,000.00 |  |  |  | GES | DoA, GSFP |
|  |  |  | Support the formation and monitoring of school clubs | ASSEC |  |  |  |  | 8,000 |  |  |  |  | GES | NCCE |
|  |  |  | Strengthen and support the guidance and counselling unit to undertake e-SHEP activities |  |  |  |  |  | 14,000.00 |  |  |  |  | GES | DA |
|  |  |  | Encourage the use of Gender Clubs and promote the use of Role models within schools and communities | Selected Schools in the District |  |  |  |  | 30,000.00 |  |  |  |  | GES | NGO |
|  |  |  | Organise Girls' week activities and advocacy | Asesewa |  |  |  |  | 40,000 |  |  |  |  | GES | DA, CSO, Media |
|  |  |  | Procure textbooks for Aseswa SHS | ASSEC |  |  |  |  | 10,000.00 |  | 150,000.00 |  |  | GES | NGO |
|  |  |  | Procure and stock libraries with books | Asesewa SHS |  |  |  |  |  |  | 120,000.00 |  |  | GES | NGO |
|  |  |  | Provide science consumables | Asesewa SHS |  |  |  |  | 100,00.00 |  |  |  |  | GES | DA |
|  |  |  | Provide technical/vocational workshops with materials | Asesewa SHS |  |  |  |  |  |  | 250,000.00 |  |  | GES | DA |
|  |  |  | Support girls in life- skills development programme at all levels | Selected schools, ASHS |  |  |  |  | 50,000.00 |  |  |  |  | GES | DA |
|  |  |  | Organise speech and prize giving days | Asesewa SHS |  |  |  |  | 30,000.00 |  |  |  |  | GES | DA |
|  |  |  | Organise STMIE clinics / fairs | Asesewa SHS |  |  |  |  | 23,000.00 |  |  |  |  | GES | DA |
|  |  |  | Monitor and evaluate teacher deployment | District wide |  |  |  |  | 30,000.00 |  |  |  |  | GES | DA |
|  |  |  | Conduct regular payroll audit in all schools to streamline staffing | All schools in the District |  |  |  |  | 30,000.00 |  |  |  |  | GES | DA |
|  |  |  | Train Heads and other teachers on ESPV Validation | Asesewa |  |  |  |  | 30,000.00 |  |  |  |  | GES | DA |
|  |  |  | Train appraisers to implement teacher appraisal system | Asesewa |  |  |  |  | 22,000.00 |  |  |  |  | GES | DA |
|  |  |  | Prepare Financial/Annual Performance Reports | Asesewa |  |  |  |  | 25,000.00 |  |  |  |  | GES | DA |
|  |  |  | Organised general monitoring and inspection of all schools | All schools in the district |  |  |  |  | 90,000.00 |  | 90,000.00 |  |  | GES | UNICEF |
|  |  |  | Organise cluster level School Performance Appraisal Meetings (SPAMs)/durbars. | All circuits |  |  |  |  | 40,000.00 |  |  |  |  | GES | UNICEF |
|  |  |  | Organise Annual Education Review | Asesewa |  |  |  |  | 30,000.00 |  |  |  |  | DA | GES |
|  |  |  | Organise workshop on the preparation of ADEOP | Asesewa |  |  |  |  | 40,000.00 |  |  |  |  | GES | UNICEF |
|  |  |  | Conduct school census | All circuits |  |  |  |  | 6,000.00 |  |  |  |  | GES | MOE/GES |
|  |  |  | Support the development of SPIP in all schools. |  |  |  |  |  |  |  | 350,000.00 |  |  | GES | UNICEF |
|  |  |  | Train DEO staff and head teachers on utilisation of school report cards and EMIS in improvement planning | Asesewa |  |  |  |  | 25,000.00 |  |  |  |  | GES | UNICEF |
|  |  |  | Organise quarterly DEOC meetings. | Asesewa |  |  |  |  | 30,000.00. |  |  |  |  | DA | GES |
|  |  |  | Train and build capacity of SMC/PTAs and PTAs on SPIP, SPAM, SRCs, gender sensitive education and special needs education. | Asesewa |  |  |  |  | 24,000.00 |  |  |  |  | GES | UNICEF |
|  |  |  | Conduct comprehensive inspection of schools. | All schools in the District |  |  |  |  | 36,000.00 |  |  |  |  | MOE/GES | DA,USAID |
|  |  |  | Conduct M & E for interventions | District wide |  |  |  |  | 30,000.00 |  |  |  |  | GES | DA |
|  |  |  | Organise Kindergarten Education Week celebration in the District | Asesewa |  |  |  |  | 20,000.00 |  |  |  |  | GES | DA |
|  |  |  | Compilation of ADPR | District Office |  | 1 |  |  | 15,000.00 |  |  |  |  | GES | DA |
|  |  |  | Confirmation and Promotion | District wide |  | 200 |  |  | 15,000.00 |  |  |  |  | GES | DA |
|  |  |  | Capitation Audit in 108 schools | All Schools | 108 |  |  |  | 15,000.00 |  |  |  |  | GES | DA |
|  |  |  | Collection of data on teachers in the District | All teachers in the district | 1233 |  |  |  | 20,000.00 |  |  |  |  | GES | DA |
|  |  |  | To enter all schools choices and continuous assessment | All school s | 1 |  |  |  | 15,000.00 |  |  |  |  | GES | DA |
|  |  |  | Picture taking and Editing | All JHS |  |  |  | 1 | 20,000.00 |  |  |  |  | GES | DA |
|  |  |  | Registration of all JHS 3students | All JHS | 1 |  |  |  | 10,000.00 |  |  |  |  | GES | DA |
|  |  |  | Student will write first mock exam in all 46 JHS | All JHS | 1 |  |  |  | 20,000.00 |  |  |  |  | GES | DA |
|  |  |  | Organise second mock exam in all 46 JHS for Students | All JHS | 1 |  |  |  | 20,000.00 |  |  |  |  | GES | DA |
| Infrastructure Delivery and Management | Infrastructure Development |  | Create 3.2km access road at Akrusu Mango Farms and Rehabilitate Trawa –Trawa Junction (4km) |  |  |  |  |  |  |  | 267,731.08 |  |  | GPSNP | DWD |
|  |  |  | Construction of pavement at Asesewa lorry park phase I. | Asesewa |  |  |  |  | 414,439.82 |  |  |  |  | DWD | DA |
|  |  |  | Construction of 4no. Culverts and 2no. 1.20m pipe culverts. | Konkoney, Mermersi, Dzomoa & (Ketedom & Esuom Manya) |  |  |  |  | 246,980.00 |  |  |  |  | DWD | DA |
|  |  |  | Construction of 1 No. canteen at Asesewa Gov’t Hospital |  |  |  |  |  | 108,238.21 |  |  |  |  | DWD | DA |
|  |  |  | Construction sectional Rigid pavement road | konkoney |  |  |  |  | 27,157.87 |  |  |  |  | DWD | DA |
|  |  |  | Supply of gravel to lorry park | Asesewa |  |  |  |  | 5,950.00 |  |  |  |  | DWD | DA |
|  |  |  | Construction of 2 additional class rooms at Asesewa community A primary school. | Asesewa |  |  |  |  | 11,461.98 |  |  |  |  | DWD | DA |
|  |  |  | Renovation of Asesewa Anglican Primary School | Asesewa |  |  |  |  | 176,102.60 |  |  |  |  | DWD | GES |
|  |  |  | Construction of 3-unit KG Classroom Pavilion at Asesewa Anglican Pavilion at Asesewa Anglican School | Asesewa |  |  |  |  | 78,000.00 |  |  |  |  | DWD | GES |
|  |  |  | Construction of 1№ 6-unit Classroom Pavilion with Office and store. | Nyoenyoem |  |  |  |  | 25,200.40 |  |  |  |  | DWD | DA, GES |
|  |  |  | Construction of 1no. 6-unit classroom block with ancillary facilities | Akotoklo-gua |  |  |  |  | 547,631.55 |  |  |  |  | DWD | DA |
|  |  |  | Construction of 1 No. 6 Unit classroom block with office and store, toilet and furniture | Akumersu Yiti |  |  |  |  | 20% of 510,824.80 (102,164.96) |  |  |  |  | DWD | GES |
|  |  |  | Construction of 1 No. teachers’ quarters with mechanized borehole | Akumersu Yiti |  |  |  |  | 20% of 278,019.70 (55,603.94) |  |  |  |  | DWD | GES |
|  |  |  | Rehabilitation of 3No. Markets | Akateng Sekesua Akrusu |  |  |  |  | 200,000.00 |  |  |  |  | DWD | DA |
|  |  |  | Completion of 3storey Office complex | Asesewa |  |  |  |  | 200,000.00 |  |  |  |  | DWD | DA |
|  |  |  | Construction of 1no. Magistrate court | Asesewa |  |  |  |  |  |  |  |  |  | DWD | DA |
|  |  |  | Construction of 1no Bungalow for District Magistrate | Asesewa |  |  |  |  |  |  |  |  |  | DWD | DA |
|  |  |  | Construction of 1no. Ambulance Bay and 4no. parking Lots for the upper Manya Krobo District Assembly | Asesewa |  |  |  |  | 5,000.00 |  |  |  |  | DWD | DA |
|  |  |  | Construction of washroom facilities for Upper Manya Krobo District Assembly (Old Block) | Asesewa |  |  |  |  | 38,417.60 |  |  |  |  | DWD | DA |
|  |  |  | Renovation and partition of office for Upper Manya Krobo District Assembly (Old Block) | Asesewa |  |  |  |  | 35,716.28 |  |  |  |  | DWD | DA |
|  |  |  | Renovation works at the DCE, DCD’s office | Asesewa |  |  |  |  | 19,836.00 |  |  |  |  | DWD | DA |
|  |  |  | Rehabilitation of DCE’s official residence | Dawa-Kolewa |  |  |  |  | 47,103.72 |  |  |  |  | DWD | DA |
|  |  |  | Renovation and maintenance of CHPS compounds | Anyaboni,Akateng, Sekesua, etc |  |  |  |  | 66,977.00 |  |  |  |  | DWD | DA |
|  |  |  | Reshaping/ sectional improvement of Aworwoso road. | Aworwoso |  |  |  |  | 149,500.00 |  |  |  |  | DWD | DA |
|  |  |  | Organize road safety Campaign | Districtwide |  |  |  |  | 5,000.00 |  |  |  |  | DWD | DA |
| Infrastructural Delivery and Management | Physical and Spatial Development |  | Document all Assembly/govt. lands and prepare comprehensive layouts | District wide |  |  |  |  | 20,000.00 |  |  |  |  | PPD | DA |
|  |  |  | Organize Monthly Spatial Committee meetings and 4No. plan education programmes | District Wide |  |  |  |  | 8,000.00 |  |  |  |  | PPD | DA |
|  |  |  | Complete Street Naming and Property Addressing | Asesewa, Akateng Sekesua |  |  |  |  | 100,000.00 |  |  |  |  | PPD | DA |
|  |  |  | Organize house to house/ communal fire safety inspections & education. | District wide |  |  |  |  | 8,000.00 |  |  |  |  | GFS | NADMO,ECG,DA |
|  |  |  | Support the operations of DVGs in 20 disaster prone zones | Selected zones |  |  |  |  |  |  |  |  |  | NADMO | DA,GES |
|  |  |  | organize anti-bush fire campaign and tree planting exercises in schools, communities, etc. |  |  |  |  |  | 2,000.00 |  |  |  |  | NADMO | DA,GES |
|  |  |  | Organize public education on climate change and its adverse effects | Selected schools |  |  |  |  | 4,000.00 |  |  |  |  | NADMO | DA, |
|  |  |  | Rehabilitation of small earth dam | Akrusu |  |  |  |  |  |  | 525,232.25 |  |  | GPSNP | DoA |
|  |  |  | Planting of 20ha of mangoes and oil palm plantation | Akrusu Anyaboni |  |  |  |  |  |  | 1,000,000 |  |  | GPSNP | DoA |
|  |  |  | Undertake DPCU, M&E activities/programmes and 2023 AAP, DESSAP preparation | UMKDA |  |  |  |  | 13,000.00 |  |  |  |  | DPU | DPCU |
|  |  |  | Preparation of 2023 District Fee-fixing & Composite Budget | UMKDA |  |  |  |  | 30,000.00 |  |  |  |  | BU | BC,DA |
|  |  |  | Organize bi-annual social accountability meetings/Town Hall meetings | Selected Towns |  |  |  |  | 60,000.00 |  |  |  |  | BU/ DPO | DA, DPCU |
|  |  |  | Provide support for Sub-structures, community initiated projects and LED activities | UMKDA |  |  |  |  | 206,052.6 |  |  |  |  | DA | DPCU |
|  |  |  | Procure office equipment, furniture and supplies | UMKDA |  |  |  |  | 13,000.00 | 5,000.00 |  |  |  | DPro | DA |
|  |  |  | Implementation of MP’s projects | District wide |  |  |  |  | 300,000.00 |  |  |  |  | MP | DA |
|  |  |  | Organise all Statutory Meetings of the Assembly | UMKDA |  |  |  |  | 40,000.00 | 45,000.00 |  |  |  | CAD | DA |
|  |  |  | Organise Capacity building for Assembly members and staff | UMKDA |  |  |  |  | 45,859.00 |  |  |  |  | HR | HoDs |
|  |  |  | Facilitate the establishment of District offices for Departments/Agencies (NHIS) | UMKDA |  |  |  |  | 20,000.00 |  |  |  |  | Mgt | DA |
| Social Service | Health Delivery |  | Support Covid-19 Interventions | UMKDA |  |  |  |  | 30,000.00 |  |  |  |  | DA | DHD |
|  |  |  | Renovation of E&T clinic into an isolation center at Gov’t Hospital | Asesewa |  |  |  |  | 39,965.60 |  |  |  |  | DWD | DA,DH |
|  |  |  | Construction of CHPs Compound | Ponponya Fantem |  |  |  |  | 63,832.53 |  |  |  |  | DWD | DA, DHD |
|  |  |  | Construction of 2 No. CHPs compound (clinic) with mechanized bore hole | Kwabia- Asasehene,Bisa |  |  |  |  | 153,096.88 |  | 375,087.36 |  |  | DWD | DA, DHD |
|  |  |  | Construction of 3No Maternity ward with borehole | Esuom-Manya, Akateng & Djamam. |  |  |  |  | 159,866.64 |  | 223,856.56 |  |  | DWD | DA, DHD |
|  |  |  | Construction of 2No Nurses quarters with borehole | Esuom Manya, Akateng, |  |  |  |  | 79,933.32 |  | 319,733.24 |  |  | DWD | DA, DHD |

UPPER MANYA KROBO DISTRICT ASSEMBLY

REVISED 2022 ANNUAL ACTION PLAN

DPCU, JUNE 2022