## Works
Procurement Entity: UPPER MANYA KROBO DISTRICT ASSEMBLY
Budget Period: JANUARY - MARCH, 2023 | [6 empty] | Tender Documents
Source of Funding: IGF/DACF/DACF-RFG/DONOR/GOG |  |  | BASIC DATA |  |  |  |  | Tendering Period |  | Tender Evaluation |  | Contract Finalization |  |  | Contract Implementation
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Pre-or Post Qualification | Final Authority for Contract Award | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Aproval by Final Authority | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
1. REHABILITATION OF SCHOOL INFRASTRACTURE | PLAN | ER/UMKDA/DACF/WKS/PQ/001/2022 | 30,000.00 | PQ |  | EH | 4/1/23 | 11/1/23 | 25/1/23 | 1/2/23 | 8/2/23 | 30,000.00 | 15/2/23 | 22/2/23 |  | 12/3/23 | 31/3/23 | 30,000.00
ACTUAL
2. REHABILITATION OF SOME SELECTED OFFICE BUILDING, MARKET, SECURITY POSTS AND HEALTH FACILITYS IN THE DISTRICT. | PLAN | ER/UMKDA/DACF & IGF/WKS/PQ/002/2023 | 23,000.00 | PQ |  | EH | 4/1/23 | 11/1/23 | 25/1/23 | 1/2/23 | 8/2/23 | 23,000.00 | 15/2/23 | 22/2/23 |  | 12/3/23 | 31/3/23 | 23,000.00
ACTUAL
3. CONSTUCTION OF MARKET SHEDS AT SEKESUA | PLAN | ER/UMKDA/DACF-RFG/WKS/NCT/003/2023 | 310,350.00 | NCT |  | ETC | 4/1/23 | 11/1/23 | 25/1/23 | 1/2/23 | 15/2/23 | 310,350.00 | 22/2/23 | 29/2/23 |  | 20/5/23 | 31/8/23 | 310,350.00
ACTUAL
4. RENOVATION OF ISOLATION CENTRE AT ASESEWA GOVERMENT HOSPITAL | PLAN | ER/UMKDA/DACF/WKS/PQ/004/2023 | 39,965.60 | PQ |  | EH | 4/1/23 | 11/1/23 | 1/2/23 | 8/2/23 | 15/2/23 | 39,965.60 | 22/2/23 | 1/3/23 |  | 8/3/23 | 15/3/23 | 39,965.60
ACTUAL
5. CONSTRUCTION OF FENCE WALL AT AKATENG MARKET (TULAKU). | PLAN | ER/UMKDA/DACF-REF/WKS/NCT/005/2023 | 350,000.00 | NCT |  | ETC | 4/1/23 | 11/1/23 | 25/1/23 | 1/2/23 | 8/2/23 | 350,000.00 | 15/2/23 | 22/2/23 | 8/3/23 | 12/4/23 | 31/5/23 | 350,000.00
ACTUAL
6. CONSTRUCTION OF SHED, SLAUGHTER SLAB & WASHROOM AT AKATENG | PLAN | ER/UMKDA/DACF-RFG/WKS/NCT/006/2023 | 160,280.68 | NCT |  | ETC | 4/1/23 | 11/1/23 | 25/1/23 | 1/2/23 | 8/2/23 | 160,280.68 | 15/2/23 | 22/2/23 | 8/3/23 | 12/5/23 | 31/8/23 | 160,280.68
ACTUAL
7. REHABILITATION AND SPOT IMPROVEMENT OF SOME SELECTED ROADS IN THE DISTRICT | PLAN | ER/UMKDA/DACF/ WKS/NCT/007/2023 | 100,000.00 | NCT |  | ETC | 4/1/23 | 11/1/23 | 25/1/23 | 1/2/23 | 8/2/23 | 100,000.00 | 15/2/23 | 22/2/23 |  | 12/3/23 | 31/3/23 | 100,000.00
ACTUAL
8. CREATE 3.2KM, ACCESS ROAD TO AKRUSU MANGO PLANTATION (GPSNP 2) | PLAN | ER/UMKDA/GPSNP/WKS/NCT/008/2023 | 600.000.00 | NCT |  | RTRCI | 4/1/23 | 11/1/23 | 1/2/23 | 8/2/23 | 15/2/23 | 600.000.00 | 22/2/23 | 1/3/23 | 8/3/23 | 12/6/23 | 15/3/23 | 600.000.00
ACTUAL
9. IMPLEMENTATION OF MP'S PROGRAMES & PROJECTS | PLAN | ER/UMKDA/DACF-MP/WKS/NCT/009/2023 | 250,000.00 | NCT |  | ETC | 4/1/23 | 11/1/23 | 25/1/23 | 1/2/23 | 8/2/23 | 250,000.00 | 22/2/23 | 1/3/23 |  | 12/6/23 | 15/3/23 | 250,000.00
ACTUAL
10. REHABILITATION OF EARTH DAM AT AYIESU (GPSNP 2) | PLAN | ER/UMKDA/GPSNP 2/WKS/NCT/010/2023 | 900,000.00 | NCT |  | ETC | 4/1/23 | 11/1/23 | 25/1/23 | 1/2/23 | 8/2/23 | 900,000.00 | 22/2/23 | 1/3/23 |  | 12/6/23 | 15/3/23 | 900,000.00
ACTUAL
11. REHABILITATION OF CHPS COMPOUND AT ANYABONI, AKATENG, SEKESUA ETC | PLAN | ER/UMKDA/DACF/WKS/PQ/011/2023 | 66,977.00 | PQ |  | EH | 4/1/23 | 11/1/23 | 1/2/23 | 8/2/23 | 15/2/23 | 66,977.00 | 22/2/23 | 1/3/23 |  | 12/3/23 | 15/3/23 | 66,977.00
ACTUAL
12. CONSTRUCTION OF OBSTETRICS & GYNECOLOGY BLOCK AT ASESEWA GOVERNMENT HOSPITAL | PLAN | ER/UMKDA/DACF/WKS/PQ/012/2023 | 58,138.21 | PQ |  | EH | 4/1/23 | 11/1/23 | 1/2/23 | 8/2/23 | 15/2/23 | 58,138.21 | 22/2/23 | 1/3/23 |  | 12/3/23 | 15/3/23 | 58,138.21
ACTUAL
13. CONSTRUCTION OF 2NO. CHIPS COMPOUND (CLINIC) WITH MECHANIZED BOREHOLE AT KWABIA ASASEHENE AND BISA (COUNTERPART FUNDING) | PLAN | ER/UMKDA/DACF/WKS/PQ/013/2023 | 107332.34 | PQ |  | EH | 4/1/23 | 4/1/23 | 1/2/23 | 8/2/23 | 15/2/23 | 107332.34 | 22/2/23 | 22/2/23 |  | 12/3/23 | 15/3/23 | 107332.34
ACTUAL
14. CONSTRUCTION OF 1NO. NHIS STANDARD CHPS COMPOUND AT AKORKOMA SISI | PLAN | ER/UMKDA/DACF/WKS/PQ/014/2023 | 40000 | PQ |  | EH | 4/1/23 | 4/1/23 | 1/2/23 | 8/2/23 | 15/2/23 | 40000 | 22/2/23 | 22/2/23 |  | 12/3/23 | 15/3/23 | 40000
ACTUAL
TOTAL | Plan |  | 2,949,638.23 | [8 empty] | 2,949,638.23 | [5 empty] | 2,949,638.23
Actual
Fill gray cells only!

## Goods
Procurement Entity: UPPER MANYA KROBO DISTRICT ASSEMBLY
Budget Period: JANUARY - MARCH, 2023 | [5 empty] | Tender Documents
Source of Funding: IGF/DACF/DACF-RFG/GOG/DONOR |  |  | BASIC DATA |  |  |  | Tendering Period |  | Tender Evaluation |  | Contract Finalization |  |  | Goods Delivery
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Final Authority for Contract Award | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing | Submission of Tender Eval Report | Approval by Final Authority | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Arrival of Goods | Inspection Final Acceptance
1. PROCUREMENT OF OFFICE EQUIPMENT AND ACCESSORIES | PLAN | ER/UMKDA/DACF & GOG/GD/PQ/001/2023 | 92300 | PQ | ETC | 4/1/23 | 11/1/23 | 25/1/23 | 8/2/23 | 22/2/23 | 92300 | 1/3/23 | 8/3/23 | 22/3/23 | 29/3/23
| ACTUAL |  | 4550 | PQ | EH | 20/2/23 | 10/3/23 | 24/3/23 | 27/3/23 | 27/3/23 | 4550 | 29/3/23 | 31/3/23 | 05/4/23 | 06/4/23
2. PURCHASE OF OFFICE SUPPLIES (STATIONERY/VALUE BOOKS/PRINTING ETC) | PLAN | ER/UMKDA/DACF & IGF/GD/PQ/002/2023 | 15000 | PQ | ETC | 4/1/23 | 11/1/23 | 25/1/23 | 8/2/23 | 22/2/23 | 15000 | 1/3/23 | 8/3/23 | 22/3/23 | 29/3/23
| ACTUAL |  | 49769.2 | PQ | EH | 13/1/23 | 16/1/23 | 30/1/23 | 01/2/23 | 03/2/23 | 49769.2 | 06/2/23 | 09/2/23 | 20/2/23 | 23/2/23
3. PROCUREMENT OF OFFICE FURNITURE & FITTINGS | PLAN | ER/UMKDA/DACF/GD/PQ/003/2023 | 70000 | PQ | ETC | 4/1/23 | 11/1/23 | 25/1/23 | 8/2/23 | 22/2/23 | 70000 | 1/3/23 | 8/3/23 | 22/3/23 | 29/3/23
ACTUAL
4. PROCUREMENT OF 1NO. REFUSE CONTAINER AND SANITARY EQUIPMENT/ DETEGENTS. | PLAN | ER/UMKDA/DACF/GD/PQ/004/2023 | 30000 | PQ | EH | 4/1/23 | 11/1/23 | 25/1/23 | 8/2/23 | 15/2/23 | 30000 | 1/3/23 | 8/3/23 | 22/3/23 | 29/3/23
ACTUAL
5. PROCUREMENT OF ITEMS FOR NATIONAL CELEBRATION (6TH MARCH) | PLAN | ER/UMKDA/DACF & IGF/GD/PQ/005/2022 | 45000 | PQ | ETC | 4/1/23 | 11/1/23 | 25/1/23 | 8/2/23 | 15/2/23 | 45000 | 1/3/23 | 8/3/23 | 22/3/23 | 29/3/23
ACTUAL
6. PROCUREMENT OF FARM INPUTS FOR NATIONAL FARMERS' DAY CELEBRATION | PLAN | ER/UMKDA/DACF & IGF/GD/PQ/006/2022 | 43000 | PQ | ETC | 4/1/23 | 11/1/23 | 25/1/23 | 8/2/23 | 22/2/23 | 43000 | 1/3/23 | 8/3/23 | 22/3/23 | 29/3/23
| ACTUAL |  | .
7. PROCUREMENT OF ITEMS TO SUPPORT PERSONS WITH DISABILITY IN VOCATION | PLAN | ER/UMKDA/GD/NCT/007/2023 | 130000 | NCT | ETC | 4/1/23 | 11/1/23 | 1/2/23 | 8/2/23 | 16/2/23 | 130000 | 23/2/23 | 1/3/23 | 15/3/23 | 22/3/23
ACTUAL
8. PROCUREMENT OF SANITARY TOOLS | PLAN | ER/UMKDA/GD/NCT/008/2023 | 4316 | PQ | EH | 4/1/23 | 11/1/23 | 25/1/23 | 8/2/23 | 22/2/23 | 4316 | 1/3/23 | 8/3/23 | 22/3/23 | 29/3/23
| ACTUAL |  | 4316 | PQ | EH | 10/1/22 | 15/1/23 | 02/2/23 | 06/2623 | 07/2/23 | 4316 | 07/2/23 | 15/2/23 | 20/2/23 | 21/2/23
TOTAL | PLAN |  | 429616 | [7 empty] | 429616
| ACTUAL |  | 58635.2 | [7 empty] | 58635.2

## Services
Procurement Entity: UPPER MANYA KROBO DISTRICT ASSEMBLY
Budget Period: JANUARY - MARCH, 2023
Source of Funding: IGF/DACF/DACF-RFG/GOG/DONOR | [5 empty] | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  | Negotiations |  |  | Contract Finalization |  |  | Contract Implementation
Contract Packages* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Selection Method | Final Authority for Contract Award | Prep & Submission by Executing Agency | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract Amount (Cedis) | Contract ward | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
1. HEALTH SCREENING OF FOOD AND DRINK VENDERS AND UNDERTAKE PUBLIC EDUCATION ON FOOD SAFETY & HYGIENE | PLAN | ER/UMKDA/IGF/PQ/TS/001/2023 | 6000 | QCBS | EH | 4/1/23 | 18/1/23 | 1/2/23 | 8/2/23 | 22/2/23 | 1/3/23 | 15/3/23 | 29/3/23 | 12/4/23 | 19/4/23 | 6000 | 26/4/23 | 4/5/23 |  | 11/5/23 | 18/5/23 | 6000
ACTUAL
2. ORGANIZE CAPACITY BUILDING TRAINING FOR STAFF, ASSEMBLY MEMBERS AND REVNUE COLLECTORS. | PLAN | ER/UMKDA/DACF-RFG/PQ/CS/002/2023 | 79.378.00 | QCBS | EH | 4/1/23 | 18/1/23 | 1/2/23 | 8/2/23 | 22/2/23 | 1/3/23 | 15/3/22 | 29/3/23 | 12/4/223 | 19/4/23 | 79.378.00 | 26/4/23 | 4/5/23 |  | 11/5/23 | 18/5/23 | 79.378.00
ACTUAL
3. MAINTENANCE AND REPAIR OF OFFICIAL VEHICLES (FUEL AND LUBRICANTS) | PLAN | ER/UMKDA/DACF & IGF/NCT/TS/003/2023 | 100000 | QCBS | ETC | 4/1/23 | 18/1/23 | 1/2/23 | 8/2/23 | 16/2/23 | 23/2/23 | 1/3/23 | 15/3/23 | 22/3/23 | 29/3/23 | 100000 | 5/4/23 | 12/4/23 |  | 3/5/23 | 17/5/23 | 100000
ACTUAL
4. ORGANIZE STREET & PROPERTY DATA BASE FOR DLRev IMPLEMENTAION AT AKATENG, OTROPKPER, SEKESUA AND AKATEWIA. | PLAN | ER/UMKDA/DACF & IGF/PQ/TS/004/2023 | 20000 | QCBS | EH | 4/1/23 | 18/1/23 | 1/2/23 | 8/2/23 | 22/2/23 | 1/3/23 | 15/3/23 | 29/3/23 | 12/4/23 | 19/4/23 | 20000 | 26/4/23 | 4/5/23 |  | 11/5/23 | 18/5/23 | 20000
ACTUAL
5. INSTALLATION OF PROPERTY ADDRESS SYSTEM & SIGNAGE | PLAN | ER/UMKDA/DACF/PQ/TS/005/2023 | 10000 | QCBS | EH | 4/1/23 | 18/1/23 | 1/2/23 | 8/2/23 | 22/2/23 | 1/3/23 | 15/3/23 | 29/3/23 | 12/4/23 | 19/4/23 | 10000 | 26/4/23 | 4/5/23 |  | 11/5/23 | 18/5/23 | 10000
ACTUAL
6. ORGANISE AND SUPERVISE REGULAR LIQUID WASTE MANAGEMENT, FUMIGATION, DISINFECTION AND DISINFESTATION OF MARKETS, SANITARY SITES, PUBLIC INSTITUTION AND FINAL DISPOSAL SITE. | PLAN | ER/UMKDA/DACF/PQ/TS/006/2023 | 80000 | QCBS | ETC | 4/1/23 | 18/1/23 | 1/2/23 | 8/2/23 | 22/2/23 | 1/3/23 | 15/3/23 | 29/3/23 | 12/4/23 | 19/4/23 | 80000 | 26/4/23 | 4/5/23 |  | 11/5/23 | 18/5/23 | 80000
ACTUAL
7. REGISTRATION AND INSTALLATION OF 7NO PILLARS ON .. ASSEMBLY LANDS AT SEKESUA, ASESEWA AND AKATENG | PLAN | ER/UMKDA/DACF/PQ/TS/007/2023 | 20000 | QCBS | EH | 4/1/23 | 18/1/23 | 1/2/23 | 8/2/23 | 22/2/23 | 1/3/23 | 15/3/23 | 29/3/23 | 12/4/23 | 19/4/23 | 20000 | 26/4/23 | 4/5/23 |  | 11/5/23 | 18/5/23
ACTUAL
Total Cost | PLAN |  | 315378 | [12 empty] | 315378 | [5 empty] | 315378
ACTUAL
Fill gray cells only!