## Works
Procurement Entity:UPPER MANYA KROBO DISTRICT ASSEMBLY
Budget Period: JANUARY- DECEMBER, 2022 | [6 empty] | Tender Documents
Source of Funding: IGF/DACF/DACF-RFG/DONOR/GOG |  |  | BASIC DATA |  |  |  |  | Tendering Period |  | Tender Evaluation |  | Contract Finalization |  |  | Contract Implementation
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Pre-or Post Qualification | Final Authority for Contract Award | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Aproval by Final Authority | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
1. FACILITATE THE EXTENSION OF ELECTRICITY TO SELECTED COMMUNITIES IN THE DISTRICT (COUNTERPART FUNDING) | Plan | ER/UMKDA/DACF/WKS/PQ/001/2022 | 30,000.00 | PQ |  | EH | 4/1/22 | 11/1/22 | 25/1/22 | 1/2/22 | 8/2/22 | 30,000.00 | 15/2/22 | 22/2/22 |  | 12/3/22 | 31/3/22 | 30,000.00
Actual
2. REHABILITATION OF SMALL EARTH DAM AT AKRUSU | Plan | ER/UMKDA/GPSNP/WKS/NCT/002/2022 | 525,232.25 | NCT |  | ETC | 4/1/22 | 11/1/22 | 25/1/22 | 1/2/22 | 22/2/22 | 525,232.25 | 25/2/22 | 29/2/22 |  | 12/8/22 | 31/12/22 | 525,232.25
Actual
3. RESHAPING OF 7.0KM ROAD AT NYAKUMASE TO AKUMASU YITI AND AFIAFE | Plan | ER/UMKDA/DACF/WKS/PQ/003/2022 | 100,000.00 | PQ |  | EH | 4/1/22 | 11/1/22 | 1/2/22 | 8/2/22 | 15/2/22 | 100,000.00 | 22/2/22 | 1/3/22 |  | 8/3/22 | 15/3/22 | 100,000.00
Actual
4. ESTABLISHMENT OF SATELLITE MARKETS AT AKRUSU AND BISA JUNCTION | Plan | ER/UMKDA/IGF/WKS/PQ/004/2022 | 70,761.50 | PQ |  | EH | 4/1/22 | 11/1/22 | 25/1/22 | 1/2/22 | 8/2/22 | 70761.5 | 15/2/22 | 22/2/22 |  | 12/3/22 | 31/3/22 | 70,761.50
Actual
5. REHABILITATION OF SELECTED MARKETS, SCHOOL BUILDINGS, CLINICS, SECURITY POSTS IN THE DISTRICT | Plan | ER/UMKDA/DACF & IGF/WKS/PQ/005/2022 | 128,761.50 | PQ |  | EH | 4/1/22 | 11/1/22 | 25/1/22 | 1/2/22 | 8/2/22 | 128,761.50 | 15/2/22 | 22/2/22 |  | 12/3/22 | 31/3/22 | 128,761.50
Actual
6. CONSTRUCTION OF 4NO. 2-BEDROOM SEMI-DETACHED FOR SENIOR STAFF AT ASESEWA | Plan | ER/UMKDA/DACF/WKS/NCT/006/2022 | 400,216.44 | NCT |  | ETC | 4/1/22 | 11/1/22 | 25/1/22 | 1/2/22 | 15/2/22 | 400,216.44 | 22/2/22 | 29/2/22 |  | 20/5/22 | 31/8/22 | 400,216.44
Actual
7. CONSTRUCTION OF 1 NO. 6-UNIT CLASSROOM BLOCK WITH ANCILARY FACILITIES AT AKOTOKLO-GUA | Plan | ER/UMKDA/DACF/WKS/NCT/007/2022 | 400,631.55 | NCT |  | ETC | 4/1/22 | 11/1/22 | 1/2/22 | 8/2/22 | 15/2/22 | 400631.55 | 22/2/22 | 1/3/22 |  | 8/3/22 | 15/3/22 | 400631.55
Actual
8. RENOVATION OF ANGLICAN PRIMARY SCHOOL AT ASESEWA | Plan | ER/UMKDA/DACF/WKS/PQ/008/2022 | 176,102.60 | PQ |  | ETC | 4/1/22 | 11/1/22 | 1/2/22 | 8/2/22 | 15/2/22 | 176,102.60 | 22/2/22 | 1/3/21 | 8/3/22 | 8/3/22 | 15/3/22 | 176,102.60
Actual
9. REPAIRS AND MAINTENANCE OF ASESEWA MARKET AND ABATTOIR | Plan | ER/UMKDA/IGF/WKS/PQ/009/2022 | 66,000.00 | PQ |  | EH | 4/1/22 | 11/1/22 | 25/1/22 | 1/2/22 | 8/2/22 | 66,000.00 | 15/2/21 | 22/2/22 |  | 12/4/22 | 31/5/22 | 66,000.00
Actual
10. CONSTRUCTION OF MODERN STRAUGHTER HOUSE AT AKETENG (TULAKU MARKET) | Plan | ER/UMKDA/DACF/WKS/PQ/010/2022 | 96,000.00 | PQ |  | EH | 4/1/22 | 11/1/22 | 25/1/22 | 1/2/22 | 8/2/22 | 96,000.00 | 15/2/22 | 22/2/22 |  | 12/5/22 | 31/8/22 | 96,000.00
Actual
11. REPAIRS AND MAINTENANCE OF ASSEMBLY'S RESIDENTIAL AND OFFICE BUILDINGS | Plan | ER/UMKDA/DACF & IGF WKS/PQ/011/2022 | 60,103.72 | PQ |  | EH | 4/1/22 | 11/1/22 | 25/1/22 | 1/2/22 | 8/2/22 | 60,103.72 | 15/2/22 | 22/2/22 |  | 12/3/22 | 31/3/22 | 60,103.72
Actual
12. REHABILITATION OF TRAWA-TRAWA JUNCTION FEEDER ROAD (4.0KM) | Plan | ER/UMKDA/GPSNP/WKS/NCT/012/2022 | 267,731.08 | NCT |  | ETC | 4/1/22 | 11/1/22 | 1/2/22 | 8/2/22 | 15/2/22 | 267,731.08 | 22/2/22 | 1/3/22 |  | 8/3/22 | 15/3/22 | 267,731.08
Actual
13. CONSTRUCTION OF POLICE STATION AT SEKESUA | Plan | ER/UMKDA/DACF/WKS/NCT/013/2022 | 200,000.00 | NCT |  | ETC | 4/1/22 | 11/1/22 | 25/1/22 | 1/2/22 | 8/2/22 | 200,000.00 | 22/2/22 | 1/3/22 |  | 12/6/22 | 31/9/22 | 200,000.00
Actual
14. IMPLEMENTATION OF MP'S PROJECTS | Plan | ER/UMKDA/DACF-MP/WKS/NCT/014/2022 | 300,000.00 | NCT |  | ETC | 4/1/22 | 11/1/22 | 25/1/22 | 1/2/22 | 8/2/22 | 300,000.00 | 22/2/22 | 1/3/22 |  | 12/6/22 | 31/9/22 | 300,000.00
Actual
15. DRILLING AND CONSTRUCTION OF BOREHOLES IN SELECTED COMMUNITIES | Plan | ER/UMKDA/DACF-RFG/WKS/NCT/015/2022 | 398,102.00 | NCT |  | ETC | 4/1/22 | 11/1/22 | 25/1/22 | 1/2/22 | 8/2/22 | 398,102.00 | 22/2/22 | 1/3/22 |  | 12/6/22 | 31/9/22 | 398,102.00
Actual
TOTAL | Plan |  | 3,219,642.64 | [8 empty] | 3,219,642.64 | [5 empty] | 3,219,642.64
Actual
Fill gray cells only!

## Goods
Procurement Entity: UPPER MANYA KROBO DISTRICT ASSEMBLY
Budget Period: JANUARY - DECEMBER, 2022 | [5 empty] | Tender Documents
Source of Funding: IGF/DACF/DACF-RFG/GOG/DONOR |  |  | BASIC DATA |  |  |  | Tendering Period |  | Tender Evaluation |  | Contract Finalization |  |  | Goods Delivery
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Final Authority for Contract Award | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing | Submission of Tender Eval Report | Approval by Final Authority | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Arrival of Goods | Inspection Final Acceptance
1. PROCUREMENT OF OFFICE EQUIPMENT | Plan | ER/UMKDA/DACF & GOG/GD/PQ/001/2022 | 65180 | PQ | ETC | 4/1/22 | 11/1/22 | 25/1/22 | 8/2/22 | 22/2/22 | 65180 | 1/3/22 | 8/3/22 | 22/3/22 | 29/3/22
Actual
2. PURCHASE OF SANITARY TOOLS | Plan | ER/UMKDA/IGF/GD/PQ/002/2022 | 1000 | PQ | EH | 4/1/22 | 11/1/22 | 25/1/22 | 8/2/22 | 15/2/22 | 1000 | 1/3/22 | 8/3/22 | 22/3/22 | 29/3/22
Actual
3. PURCHASE OF OFFICE SUPPLIES (STATIONERY/VALUE BOOKS/PRINTING ETC) | Plan | ER/UMKDA/DACF & IGF/GD/PQ/003/2022 | 50092 | PQ | ETC | 4/1/22 | 11/1/22 | 25/1/22 | 8/2/22 | 22/2/22 | 50092 | 1/3/22 | 8/3/22 | 22/3/22 | 29/3/22
Actual
4. PROCUREMENT OF OFFICE FURNITURE & FITTINGS | Plan | ER/UMKDA/DACF/GD/PQ/004/2022 | 70000 | PQ | ETC | 4/1/22 | 11/1/22 | 25/1/22 | 8/2/22 | 22/2/22 | 70000 | 1/3/22 | 8/3/22 | 22/3/22 | 29/3/22
Actual
5. PROCUREMENT OF 4 NO. REFUSE CONTAINERS FOR OTROKPER, SEKESUA, AKRUSU AND AKATENG | Plan | ER/UMKDA/DACF/GD/PQ/005/2022 | 50000 | PQ | EH | 4/1/22 | 11/1/22 | 25/1/22 | 8/2/22 | 15/2/22 | 50000 | 1/3/22 | 8/3/22 | 22/3/22 | 29/3/22
Actual
6. PROCUREMENT OF ITEMS FOR NATIONAL CELEBRATION (6TH MARCH) | Plan | ER/UMKDA/DACF & IGF/GD/PQ/006/2022 | 60000 | PQ | ETC | 4/1/22 | 11/1/22 | 25/1/22 | 8/2/22 | 15/2/22 | 60000 | 1/3/22 | 8/3/22 | 22/3/22 | 29/3/22
Actual
7. PROCUREMENT OF FARM INPUTS FOR NATIONAL FARMERS' DAY CELEBRATION | Plan | ER/UMKDA/DACF & IGF/GD/PQ/007/2022 | 55000 | PQ | ETC | 4/1/22 | 11/1/22 | 25/1/22 | 8/2/22 | 22/2/22 | 55000 | 1/3/22 | 8/3/22 | 22/3/22 | 29/3/22
| Actual |  | .
8. PROCUREMENT OF COVID-19 PPE'S | Plan | ER/UMKDA/DACF/GD/PQ/008/2022 | 30000 | PQ | EH | 4/1/22 | 11/1/22 | 1/2/22 | 8/2/22 | 16/2/22 | 30000 | 23/2/22 | 1/3/22 | 15/3/22 | 22/3/22
Actual
9. PROCUREMENT OF ITEMS FOR PERSONS WITH DISABILITY | Plan | ER/UMKDA/GD/NCT/009/2022 | 206052.6 | NCT | ETC | 4/1/22 | 11/1/22 | 1/2/22 | 8/2/22 | 16/2/22 | 206052.6 | 23/2/22 | 1/3/22 | 15/3/22 | 22/3/22
Actual
10. SUPPLY OF BUILDING MATERIALS TO SUPPORT COMMUNITY INITIATED PROJECTS | Plan | ER/UMKDA/DACF/GD/NCT/010/2022 | 206052.6 | NCT | ETC | 1/2/22 | 8/2/22 | 22/2/22 | 8/3/22 | 16/3/22 | 206052.6 | 23/3/22 | 5/4/22 | 19/4/22 | 26/4/22
Actual
TOTAL | Plan |  | 793377.2 | [7 empty] | 793377.2
Actual

## Services
Procurement Entity: UPPER MANYA KROBO DISTRICT ASSEMBLY
Budget Period: JANUARY - DECEMBER, 2022
Source of Funding: IGF/DACF/DACF-RFG/GOG/DONOR | [5 empty] | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  | Negotiations |  |  | Contract Finalization |  |  | Contract Implementation
Contract Packages* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Selection Method | Final Authority for Contract Award | Prep & Submission by Executing Agency | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract Amount (Cedis) | Contract ward | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
1. EVACUATION OF THREE MOUNTAINOUS REFUSE DUMP AT SEKESUA, ASESEWA AND OTROKPER | Plan | ER/UMKDA/PQ/TS/001/2022 | 50000 | QCBS | EH | 4/1/22 | 18/1/22 | 1/2/22 | 8/2/22 | 22/2/22 | 1/3/22 | 15/3/22 | 29/3/22 | 12/4/22 | 19/4/22 | 50000 | 26/4/22 | 4/5/22 |  | 11/5/22 | 18/5/22 | 50000
Actual
2. HEALTH SCREENING OF FOOD AND DRINK VENDERS IN THE DISTRICT (COUNTERPART FUNDING) | Plan | ER/UMKDA/IGF/PQ/TS/002/2022 | 1000 | QCBS | EH | 4/1/22 | 18/1/22 | 1/2/21 | 8/2/22 | 22/2/22 | 1/3/22 | 15/3/22 | 29/3/22 | 12/4/22 | 19/4/22 | 1000 | 26/4/22 | 4/5/22 |  | 11/5/22 | 18/5/22 | 1,000.00
Actual
3. FUMIGATION, DISINFECTION AND DISINFESTATION OF MARKETS AND SANITARY SITES | Plan | ER/UMKDA/DACF/ PQ/TS/003/2022 | 10000 | QCBS | EH | 4/1/22 | 18/1/22 | 1/2/22 | 8/2/22 | 22/2/22 | 1/3/22 | 15/3/22 | 29/3/22 | 12/4/22 | 19/4/22 | 10000 | 26/4/22 | 4/5/22 |  | 11/5/22 | 18/5/22 | 10,000.00
Actual
4. REVALUATION OF PROPERTIES IN THE DISTRICT | Plan | ER/UMKDA/DACF/PQ/TS/004/2022 | 20000 | QCBS | EH | 4/1/22 | 18/1/22 | 1/2/22 | 8/2/22 | 22/2/22 | 1/3/22 | 15/3/22 | 29/3/22 | 12/4/22 | 19/4/22 | 20000 | 26/4/22 | 4/5/22 |  | 11/5/22 | 18/5/22 | 20,000.00
Actual
5. ORGANIZE CAPACITY BUILDING TRAINING FOR STAFF | Plan | ER/UMKDA/DACF-RFG/PQ/TS/005/2022 | 45859 | QCBS | EH | 4/1/22 | 18/1/22 | 1/2/22 | 8/2/22 | 22/2/22 | 1/3/22 | 15/3/22 | 29/3/22 | 12/4/22 | 19/4/22 | 45859 | 26/4/22 | 4/5/22 |  | 11/5/22 | 18/5/22 | 45859
Actual
6. MAINTENANCE OF OFFICIAL VEHICLES | Plan | ER/UMKDA/DACF & IGF/NCT/TS/006/2022 | 140000 | QCBS | ETC | 4/1/22 | 18/1/22 | 1/2/22 | 8/2/22 | 16/2/21 | 23/2/22 | 1/3/22 | 15/3/22 | 22/3/22 | 29/3/22 | 140000 | 5/4/22 | 12/4/22 |  | 3/5/22 | 17/5/22 | 140000
Actual
7. ACQUIRE INSURANCE FOR ASSEMBLY PROPERTIES | Plan | ER/UMKDA/DACF & IGF/PQ/TS/007/2022 | 22000 | QCBS | EH | 4/1/22 | 18/1/22 | 1/2/22 | 8/2/22 | 22/2/22 | 1/3/22 | 15/3/22 | 29/3/22 | 12/4/22 | 19/4/22 | 22000 | 26/4/22 | 4/5/22 |  | 11/5/22 | 18/5/22 | 22000
Actual
8. REPAIR AND MAINTENANCE OF OFFICE EQUIPMENT | Plan | ER/UMKDA/IGF/PQ/TS/008/2022 | 10000 | QCBS | EH | 4/1/22 | 18/1/22 | 1/2/22 | 8/2/22 | 22/2/22 | 1/3/22 | 15/3/22 | 29/3/22 | 12/4/22 | 19/4/22 | 10000 | 26/4/22 | 4/5/22 |  | 11/5/22 | 18/5/22 | 10000
Actual
9. STREET NAMING AND PROPERTY ADDRESSING DISTRICT WIDE | Plan | ER/UMKDA/DACF/PQ/TS/009/2022 | 20000 | QCBS | EH | 4/1/22 | 18/1/22 | 1/2/22 | 8/2/22 | 22/2/22 | 1/3/22 | 15/3/22 | 29/3/22 | 12/4/22 | 19/4/22 | 20000 | 26/4/22 | 4/5/22 |  | 11/5/22 | 18/5/22 | 20000
Actual
10. ACQUISITION OF LAND/REGISTRATION OF ASSEMBLY PROPERTIES | Plan | ER/UMKDA/DACF/PQ/TS/010/2022 | 40000 | QCBS | EH | 4/1/22 | 18/1/22 | 1/2/22 | 8/2/22 | 22/2/22 | 1/3/22 | 15/3/22 | 29/3/22 | 12/4/22 | 19/4/22 | 40000 | 26/4/22 | 4/5/22 |  | 11/5/22 | 18/5/22 | 40000
Actual
Total Cost | Plan |  | 418859 | [12 empty] | 418859 | [5 empty] | 418859
Actual
Fill gray cells only!