## Works
Procurement Entity: UPPER MANYA KROBO DISTRICT ASSEMBLY
Budget Period: JANUARY-DECEMBER, 2024 | [6 empty] | Tender Documents
Source of Funding: IGF/DACF/DACF-RFG/DONOR/GOG |  |  | BASIC DATA |  |  |  |  | Tendering Period |  | Tender Evaluation |  | Contract Finalization |  |  | Contract Implementation
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Pre-or Post Qualification | Final Authority for Contract Award | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing-Opening | Submission Tender Eval Rpt | Aproval by Final Authority | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
1. CONSTRUCTION OF 1N0. 6 UNIT CLASSROOM BLOCK WITH OFFICE & STORE, TOILET AND FURNITURE AT AKUMERSU YITI | PLAN | ER/UMKDA/DACF/WKS/NCT/001/2024 | 62,165.03 | NCT |  | EH | 4/1/24 | 11/1/24 | 25/1/24 | 1/2/24 | 15/2/24 | 62,165.03 | 22/2/24 | 29/2/24 |  | 20/5/24 | 31/8/24 | 62,165.03
ACTUAL
2. RENOVATION OF ANGLICAN PRIMARY SCHOOL ASESEWA | PLAN | ER/UMKDA/DACF/WKS/NCT/002/2024 | 106,102.60 | NCT |  | ETC | 4/1/24 | 11/1/24 | 1/2/24 | 8/2/24 | 15/2/24 | 106,102.60 | 22/2/24 | 1/3/24 |  | 8/3/24 | 15/3/24 | 106,102.60
ACTUAL
3. REHABILITATION OF SCHOOL INFRASTRUCTURE | PLAN | ER/UMKDA/IGF-DACF/WKS/PQ/003/2024 | 41,947.17 | PQ |  | EH | 4/1/24 | 11/1/24 | 25/1/24 | 1/2/24 | 8/2/24 | 41947.17 | 15/2/24 | 22/2/24 | 8/3/24 | 12/4/24 | 31/5/24 | 41,947.17
ACTUAL
4. CONSTRUCTION OF FIRE TENDER BAY | PLAN | ER/UMKDA/DACF/WKS/PQ/004/2024 | 50,000.00 | PQ |  | ETC | 4/1/24 | 11/1/24 | 25/1/24 | 1/2/24 | 8/2/24 | 50,000.00 | 15/2/24 | 22/2/24 | 8/3/24 | 12/5/24 | 31/8/24 | 50,000.00
ACTUAL
5. CONSTRUCTION OF 2N0. CHIPs COMPOUND (CLINIC) WITH MECHANIZED BOREHOLE (ALL SIF COUNTERPART FUNDING) | PLAN | ER/UMKDA/DACF/ WKS/NCT/005/2024 | 104,957.35 | NCT |  | ETC | 4/1/2 | 11/1/24 | 25/1/24 | 1/2/24 | 8/2/24 | 104,957.35 | 15/2/24 | 22/2/24 |  | 12/3/24 | 31/3/24 | 104,957.35
ACTUAL
6. REHABILITATION OF AKRUSU JUCTION- ASEKESO FEEDER ROAD (3.64 KM) | PLAN | ER/UMKDA/GPSNP/WKS/NCT/006/2024 | 650,000.00 | NCT |  | RTRC | 4/1/24 | 11/1/24 | 1/2/24 | 8/2/24 | 15/2/24 | 650,000.00 | 22/2/24 | 1/3/24 | 8/3/24 | 12/6/24 | 15/3/24 | 650,000.00
ACTUAL
7. IMPLEMENTATION OF MP'S PROGRAMES & PROJECTS | PLAN | ER/UMKDA/DACF-MP/WKS/PQ/007/2024 | 230,000.00 | NCT |  | ETC | 4/1/24 | 11/1/24 | 25/1/24 | 1/2/24 | 8/2/24 | 230,000.00 | 22/2/24 | 1/3/24 |  | 12/6/24 | 15/3/24 | 230,000.00
ACTUAL
8. CONSTRUCTION OF FENCE WALL AT TULAKU COW MARKET, AKATENG | PLAN | ER/UMKDA/DACF-RFG/WKS/NCT/008/2024 | 388,060.08 | NCT |  | ETC | 4/1/24 | 11/1/24 | 25/1/24 | 1/2/24 | 8/2/24 | 388,060.08 | 22/2/24 | 1/3/24 |  | 12/6/24 | 15/3/24 | 388,060.08
ACTUAL
9. CONSTRUCTION OF 1N0. 24 UNIT MARKET SHED AT SEKESUA | PLAN | ER/UMKDA/DACF-RFG/WKS/PQ/009/2024 | 329,525.92 | NCT |  | ETC | 4/1/23 | 11/1/23 | 1/2/23 | 8/2/23 | 15/2/23 | 329,525.92 | 22/2/23 | 1/3/23 |  | 12/3/23 | 15/3/23 | 329,525.92
ACTUAL
10. CONSTRUCTION OF SHED, SLUGHTER SLAB AND WASHROOM AT AKATENG | PLAN | ER/UMKDA/IGF/WKS/PQ/010/2024 | 160,280.65 | NCT |  | ETC | 4/1/24 | 11/1/24 | 1/2/24 | 8/2/24 | 15/2/24 | 160,280.65 | 22/2/24 | 1/3/24 |  | 12/3/24 | 15/3/24 | 160,280.65
ACTUAL
11. REHABILITATION AND SPOT IMPROVEMENT OF SELECTED ROADS | PLAN | ER/UMKDA/DACF/WKS/NCT/011/2024 | 100000 | NCT |  | ETC | 4/1/24 | 4/1/24 | 1/2/24 | 8/2/24 | 15/2/24 | 100000 | 22/2/24 | 22/2/24 |  | 12/3/24 | 15/3/24 | 100000
ACTUAL
12.REHABILITATION OF OFFICE BUILDING, MARKETS, SECURITY AND HEALTH FACILITIES | PLAN | ER/UMKDA/IGF-DACF/WKS/PQ/012/2024 | 53,000.00 | PQ |  | ETC | 4/1/24 | 11/1/24 | 25/1/24 | 1/2/24 | 8/2/24 | 53,000.00 | 15/2/24 | 22/2/24 | 8/3/24 | 12/4/24 | 31/5/24 | 53,000.00
ACTUAL
TOTAL | Plan |  | 2,276,038.80 | [8 empty] | 2,276,038.80 | [5 empty] | 2,276,038.80
Actual
Fill gray cells only!

## Goods
Procurement Entity: UPPER MANYA KROBO DISTRICT ASSEMBLY
Budget Period: JANUARY - DECEMBER, 2024 | [5 empty] | Tender Documents
Source of Funding: IGF/DACF/DACF-RFG/GOG/DONOR |  |  | BASIC DATA |  |  |  | Tendering Period |  | Tender Evaluation |  | Contract Finalization |  |  | Goods Delivery
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Final Authority for Contract Award | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing | Submission of Tender Eval Report | Approval by Final Authority | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Arrival of Goods | Inspection Final Acceptance
1. PROCUREMENT OF OFFICE EQUIPMENT, CONSUMABLES AND ACCESSORIES | PLAN | ER/UMKDA/DACF & GOG/GD/PQ/001/2024 | 27000 | PQ | EH | 4/1/24 | 11/1/24 | 25/1/24 | 8/2/24 | 22/2/24 | 27000 | 1/3/24 | 8/3/24 | 22/3/24 | 2/4/24
ACTUAL
2. PURCHASE OF OFFICE STATIONERY, VALUE BOOKS AND PRINTING | PLAN | ER/UMKDA/DACF-IGF-GOG/GD/PQ/002/2024 | 65000 | PQ | ETC | 4/1/24 | 11/1/24 | 25/1/24 | 8/2/24 | 22/2/24 | 65000 | 1/3/24 | 8/3/24 | 22/3/24 | 2/4/24
ACTUAL
3. PROCUREMENT OF OFFICE FURNITURE & FITTINGS | PLAN | ER/UMKDA/GOG/DACF/GD/PQ/003/2024 | 44000 | PQ | EH | 4/1/24 | 11/1/24 | 25/1/24 | 8/2/24 | 22/2/24 | 44000 | 1/3/24 | 8/3/24 | 22/3/24 | 2/4/24
ACTUAL
4. PROCUREMENT OF ITEMS FOR NATIONAL CELEBRATION (6TH MARCH) | PLAN | ER/UMKDA/DACF & IGF/GD/PQ/004/2024 | 45000 | PQ | EH | 4/1/24 | 11/1/24 | 25/1/24 | 8/2/24 | 15/2/24 | 45000 | 1/3/24 | 8/3/24 | 22/3/24 | 2/4/24
ACTUAL
5. PROCUREMENT OF FARM INPUTS FOR NATIONAL FARMERS' DAY CELEBRATION | PLAN | ER/UMKDA/DACF & IGF/GD/PQ/005/2024 | 63000 | PQ | ETC | 4/1/24 | 11/1/24 | 25/1/24 | 8/2/24 | 22/2/24 | 63000 | 1/3/24 | 8/3/24 | 22/3/24 | 2/4/24
| ACTUAL |  | .
TOTAL | PLAN |  | 244000 | [7 empty] | 244000
ACTUAL

## Services
Procurement Entity: UPPER MANYA KROBO DISTRICT ASSEMBLY
Budget Period: JANUARY - DECEMBER, 2024
Source of Funding: IGF/DACF/DACF-RFG/GOG/DONOR | [5 empty] | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  | Negotiations |  |  | Contract Finalization |  |  | Contract Implementation
Contract Packages* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Selection Method | Final Authority for Contract Award | Prep & Submission by Executing Agency | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract Amount (Cedis) | Contract ward | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
1. HEALTH SCREENING OF FOOD AND DRINK VENDERS AND UNDERTAKE PUBLIC EDUCATION ON FOOD SAFETY & HYGIENE | PLAN | ER/UMKDA/IGF/PQ/TS/001/2024 | 16000 | QCBS | EH | 4/1/24 | 18/1/24 | 1/2/24 | 8/2/24 | 22/2/24 | 1/3/24 | 15/3/24 | 2/4/24 | 12/4/24 | 19/4/24 | 16000 | 26/4/24 | 3/5/24 |  | 10/5/24 | 17/5/24 | 16000
ACTUAL
2. ORGANIZE CAPACITY BUILDING TRAINING FOR STAFF, ASSEMBLY MEMBERS AND REVNUE COLLECTORS. | PLAN | ER/UMKDA/DACF-RG&IGF/PQ/CS/002/2024 | 33000 | QCBS | EH | 4/1/24 | 18/1/24 | 1/2/24 | 8/2/24 | 22/2/24 | 1/3/24 | 15/3/24 | 2/4/24 | 12/4/24 | 19/4/24 | 33000 | 26/4/24 | 3/5/24 |  | 10/5/24 | 17/5/24 | 33000
ACTUAL
3. MAINTENANCE OF OFFICIAL VEHICLES, FUEL AND LUBRICANTS | PLAN | ER/UMKDA/DACF & IGF/NCT/TS/003/2024 | 90000 | QCBS | ETC | 4/1/24 | 18/1/24 | 1/2/24 | 8/2/24 | 16/2/24 | 23/2/24 | 1/3/24 | 2/4/24 | 22/3/24 | 29/3/24 | 90000 | 5/4/24 | 3/5/24 |  | 10/5/24 | 17/5/24 | 90000
ACTUAL
4.UNDERTAKE PROPERTY EMBORSEMENT EXERCISE | PLAN | ER/UMKDA/DACF & IGF/PQ/TS/004/2024 | 20000 | QCBS | EH | 4/1/24 | 18/1/24 | 1/2/24 | 8/2/24 | 22/2/24 | 1/3/24 | 15/3/24 | 2/4/24 | 12/4/24 | 19/4/24 | 20000 | 26/4/24 | 3/5/24 |  | 10/5/24 | 17/5/24 | 20000
ACTUAL
5. INSTALL PROPERTY ADDRESS & SYNAGE | PLAN | ER/UMKDA/DACF/PQ/TS/005/2024 | 10000 | QCBS | EH | 4/1/24 | 18/1/24 | 1/2/24 | 8/2/24 | 22/2/24 | 1/3/24 | 15/3/24 | 2/4/24 | 12/4/24 | 19/4/24 | 10000 | 26/4/24 | 3/5/24 |  | 10/5/24 | 17/5/24 | 10000
ACTUAL
6. ORGANISE AND SUPERVISE REGULAR LIQUID WASTE MANAGEMENT, FUMIGATION, DISINFECTION AND DISINFESTATION OF MARKETS, SANITARY SITES, PUBLIC INSTITUTION AND FINAL DISPOSAL SITE. | PLAN | ER/UMKDA/DACF/PQ/TS/006/2024 | 120000 | QCBS | ETC | 4/1/24 | 18/1/24 | 1/2/24 | 8/2/24 | 22/2/24 | 1/3/24 | 15/3/24 | 2/4/24 | 12/4/24 | 19/4/24 | 120000 | 26/4/24 | 3/5/24 |  | 10/5/24 | 17/5/24 | 120000
ACTUAL
Total Cost | PLAN |  | 289000 | [12 empty] | 289000 | [5 empty] | 289000
ACTUAL
Fill gray cells only!